## DILG-1st qtr
FDPP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1ST QUARTER, CY 2018
Province, City or Municipality: Gloria, Oriental Mindoro
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT SECTOR
Social Welfare Services
Senior Citizens Hall-Maligaya | Maligaya | 384682.34 | 1-25-2018 | 12-31-2018 | 88.2% | 339283
Rehabilitation and Improvement of Senior Citizen Multi-Purpose Buildings | Maligaya | 33250 | 1-12-2017 | 12-31-2018 | 94.65% | 31472.5
Construction of Multi-Purpose Building-cum-Evacuation Center in Sta. Maria and Narra | Sta. Maria and Narra | 1300000 | 12-13-2017 | 12-31-2018 | 62.52% | 812770
Purchase of Relocation Land for the Landless Indigent Families (70% Municipal Counterpart) | various barangays | 322000 | 9-11-2014 | 12-31-2018 | 68.32% | 220000
Educational Service
Construction & Establishment of Manpower Development Center (Tech-Voc School/GSAT) | Maligaya | 169864.15 | 6-9-2015 | 12-31-2018 | 12.85% | 21825
Health services
Completion of RHU Building (Formerly Medicare Hospital) | Maligaya | 1005079.2 | 6-17-2016 | 12-31-2018 | 67.03% | 673747
Placenta pit constructed | Maligaya | 33891 | 5-12-2017 | 6-30-2018 | 17.04% | 5775
ECONOMIC SERVICES SECTOR
Environmental Management Service
Suma-Landfill Nawa (SLN) ang Basura ng Gloria Project (Operation of Sanitary Landfill Category I) | Agos | 2000000 | 2-27-2018 | 12-31-2018 | 16.1% | 321973.38
Acquisition & Development of Landfill | Agos | 708026.62 | 3-23-2017 | 12-31-2018 | 100% | 708026.62
Engineering Services - Construction and Maintenance
Concreting of Municipal Road/Municipal Streets | various barangays | 260467.28 | 10-10-2017 | 12-22-2018 | 59.33% | 154544.56
Agriculture Services
Construction of Concrete Irrigation Canal | G.Antonino,Banutan & Manguyang | 179000 | 2-27-2018 | 12-31-2018 | 99.64% | 178360.1
TOTAL |  | 6396260.59 |  |  |  | 3467777.16
Prepared by: |  |  |  |  | Certified correct:
SHERALEEN C. ABUAN | [5 empty] | GERMAN D. RODEGERIO
Municipal Budget Officer | [5 empty] | Municipal Mayor
Note on C7: Gloria: APPROPRIATION/ bal.of 2017