## Sheet1
FDPP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1st QUARTER, CY 2019
Province, City or Municipality: Gloria, Oriental Mindoro
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date |  |  |  | 49200
ECONOMIC SERVICES SECTOR
Engineering Services - Construction and Maintenance
Establishment of Municipal Museum | Maligaya,Gloria | 151664 | 8-15-18 | 12-30-18 | 99.67% | 151160
Capital Expenditure for Local Economic Development Project: Improvement of Municipal Plaza-cum-Kubotel | Maligaya,Gloria | 1069814.5 |  |  | 99.9% | 1068788.5
Construction of Sitio Townsite Multi-Purpose Hall at Brgy. Malubay | Brgy.Malubay | 131464 | 10-9-18 | 12-26-18 | 97.76% | 128525
Construction of Multi-Purpose Building-cum-Evacuation Center at Sta. Maria Phase II(2018) | Brgy.Sta. Maria | 12650 | 10-10-2017 | 12-22-2018 | 100% | 12650
Sta. Theresa Protection Dike | Brgy. Sta.Theresa | 500000 | 7-12-18 | 12-28-18 | 99.92% | 499620
Drainage Canal Construction | Brgy. Bulaklakan | 127095.03 | 7-20-18 | 12-28-18 | 97.83% | 124336.1
Capital Expenditure for Livelihood Projects(2018) | Mun.farm Maligaya,Gloria | 82692.42 | 7-20-18 | 12-28-18 | 96.9% | 80132.5
Const. of MP Hall - Sta Maria | Brgy.Sta. Maria | 556299.2 | 5-28-19 | 12-31-19 | 69.87% | 388690
Construction of Bulakalakan MP-Hall | Brgy. Bulaklakan | 140000 | 8-10-18 | 12-20-18 | 99.8% | 139719.6
Rehab & Improve SC Hall - Sta Theresa | Brgy. Sta.Theresa | 250000 | 8-05-18 | 12-30-18 | 99.9% | 249739
Drainage Canal Construction - Alma Villa | Brgy. Alma Villa | 250000 | 1-20-18 | 12-31-18 | 99.9% | 249739
Municipal Counterpart for LGU-Led KC-NCDDP Implementation of Sub-Projects | Various brgys. | 2880000 | 11-15-18 | 12-31-18 | 84.49% | 2433268.12
Agriculture Services
Capital Expenditure for Livelihood Projects(2015) | Maligaya Gloria | 157180 | 8-05-18 | 12-30-18 | 100% | 157180
TOTAL |  | 6308859.15 |  |  |  | 5683547.82 |  |  | 840000
194941
Prepared by: |  |  |  |  | Certified correct: |  |  |  | 645059
1120000
#REF!
SHERALEEN C. ABUAN | [5 empty] | GERMAN D. RODEGERIO
Municipal Budget Officer | [5 empty] | Municipal Mayor
Note on C7: Gloria: APPROPRIATION/ bal.of dec. 31 2018