## 3rd tr
FDPP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 3rd QUARTER, CY 2018
Province, City or Municipality: Gloria, Oriental Mindoro
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date | [5 empty] | 49200
SOCIAL DEVELOPMENT SECTOR | [11 empty] | 26965
126290
Social Welfare Services
Senior Citizens Hall-Maligaya | Maligaya | 384682.34 | 1-25-2018 | 12-31-2018 | 99.97% | 384583
Rehabilitation and Improvement of Senior Citizen Multi-Purpose Buildings | Maligaya | 33250 | 1-12-2017 | 12-31-2018 | 104.3% | 34672.5 |  |  | -1422.5 | 697470.99 | 217140 | 50650
Construction of Multi-Purpose Building-cum-Evacuation Center in Sta. Maria and Narra | Sta. Maria and Narra | 1300000 | 12-13-2017 | 12-31-2018 | 70.58% | 917515
Purchase of Relocation Land for the Landless Indigent Families (70% Municipal Counterpart) | various barangays | 322000 | 9-11-2014 | 12-31-2018 | 68.32% | 220000
Educational Service
Construction & Establishment of Manpower Development Center (Tech-Voc School/GSAT) | Maligaya | 169864.15 | 6-9-2015 | 12-31-2018 | 12.85% | 21825
Health services
Completion of RHU Building (Formerly Medicare Hospital) | Maligaya | 1005079.2 | 6-17-2016 | 12-31-2018 | 75.63% | 760172
Placenta pit constructed | Maligaya | 33891 | 5-12-2017 | 6-30-2018 | 17.04% | 5775
ECONOMIC SERVICES SECTOR
Environmental Management Service
Suma-Landfill Nawa (SLN) ang Basura ng Gloria Project (Operation of Sanitary Landfill Category I) | Agos | 2000000 | 2-27-2018 | 12-31-2018 | 19.79% | 395800.17
Acquisition & Development of Landfill | Agos | 708026.62 | 3-23-2017 | 12-31-2018 | 100% | 708026.62
Engineering Services - Construction and Maintenance
Additional KC-NCDDP Tier 2 Counterpart | var. brgys. | 1218158.08 | 8-15-18 | 12-30-18 | 88.39% | 1076757.85
Repair of Ikot Bayan Tricycle Terminal | Pob. Public Market | 42849.22 | 10-9-18 | 12-26-18 | 72.38% | 31016
Concreting of Municipal Road/Municipal Streets | various barangays | 260467.28 | 10-10-2017 | 12-22-2018 | 74.31% | 193544.56
Capt. Exp. For local Economic Dev. Proj.Mun.Plaza-Kubotel | Mun. Plaza/Mun.Oval | 3900000 | 7-12-18 | 12-28-18 | 67.36% | 2626985.5
Conts.of Mun.Cemetery Drainage Canal | Mun.Cemeteryat Balagbag Maligaya | 500000 | 7-20-18 | 12-28-18 | 70.74% | 353699
Conts.of Apartment type niches | Mun.Cemeteryat Balagbag Maligaya | 30000 | 7-20-18 | 12-28-18 | 987% | 296094.16
Repair of Rehab of Public Marketstalls | Pub. Market at Pob. Gloria | 700000 | 8-10-18 | 12-20-18 | 72.86% | 510050
Improvement of Phantom Cave | Bgry. Malubay | 66614.9 | 8-05-18 | 12-30-18 | 78.01% | 51965
Agriculture Services
Maint. Improvement of Mangrove area | var.coastal brgys. | 75000 | 8-05-18 | 12-30-18 | 78.44% | 58830
Construction of PIG PEN | Mun. Farm | 117392.04 | 9-21-18 | 12-30-18 | 99.8% | 117160
Construction of Concrete Irrigation Canal | G.Antonino,Banutan & Manguyang | 179000 | 2-27-2018 | 12-31-2018 | 99.64% | 178360.1
TOTAL |  | 13046274.83 |  |  |  | 8942831.46 |  |  |  | 840000
194941
Prepared by: |  |  |  |  | Certified correct: |  |  |  |  | 645059
1120000
#REF!
SHERALEEN C. ABUAN | [5 empty] | GERMAN D. RODEGERIO
Municipal Budget Officer | [5 empty] | Municipal Mayor

## 4th qtr 2018
FDPP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2018
Province, City or Municipality: Gloria, Oriental Mindoro
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date | [5 empty] | 49200
SOCIAL DEVELOPMENT SECTOR | [11 empty] | 26965
126290
Social Welfare Services
Senior Citizens Hall-Maligaya | Maligaya | 384682.34 | 1-25-2018 | 12-31-2018 | 99.97% | 384583
Rehabilitation and Improvement of Senior Citizen Multi-Purpose Buildings | Maligaya | 33250 | 1-12-2017 | 12-31-2018 | 104.3% | 34672.5 |  |  | -1422.5 | 697470.99 | 217140 | 50650
Construction of Multi-Purpose Building-cum-Evacuation Center in Sta. Maria and Narra | Sta. Maria and Narra | 1300000 | 12-13-2017 | 12-31-2018 | 99.16% | 1289030
Purchase of Relocation Land for the Landless Indigent Families (70% Municipal Counterpart) | various barangays | 322000 | 9-11-2014 | 12-31-2018 | 68.32% | 220000
Educational Service
Construction & Establishment of Manpower Development Center (Tech-Voc School/GSAT) | Maligaya | 169864.15 | 6-9-2015 | 12-31-2018 | 12.85% | 21825
Health services
Completion of RHU Building (Formerly Medicare Hospital) | Maligaya | 1005079.2 | 6-17-2016 | 12-31-2018 | 75.63% | 760172
Placenta pit constructed | Maligaya | 33891 | 5-12-2017 | 6-30-2018 | 17.04% | 5775
ECONOMIC SERVICES SECTOR
Environmental Management Service
Suma-Landfill NAWA (SLN) | Agos | 2000000 | 8-05-18 | 12-31-18 | 14.59% | 291751.45
Suma-Landfill Nawa (SLN) ang Basura ng Gloria Project (Operation of Sanitary Landfill Category I) | Agos | 2000000 | 2-27-2018 | 12-31-2018 | 96.89% | 1937793.43
Acquisition & Development of Landfill | Agos | 708026.62 | 3-23-2017 | 12-31-2018 | 100% | 708026.62
Engineering Services - Construction and Maintenance
Additional KC-NCDDP Tier 2 Counterpart | var. brgys. | 1218158.08 | 8-15-18 | 12-30-18 | 88.39% | 1076757.85
Repair of Ikot Bayan Tricycle Terminal | Pob. Public Market | 55193.44 | 10-9-18 | 12-26-18 | 133.1% | 73482
Concreting of Municipal Road/Municipal Streets | various barangays | 260467.28 | 10-10-2017 | 12-22-2018 | 575.6% | 1499281.88
Capt. Exp. For local Economic Dev. Proj.Mun.Plaza-Kubotel | Mun. Plaza/Mun.Oval | 4050000 | 7-12-18 | 12-28-18 | 73.58% | 2980185.5
Conts.of Mun.Cemetery Drainage Canal | Mun.Cemetery at Balagbag Maligaya | 500000 | 7-20-18 | 12-28-18 | 70.74% | 353699
Conts.of Apartment type niches | Mun.Cemeteryat Balagbag Maligaya | 30000 | 7-20-18 | 12-28-18 | 987% | 296094.16
Repair of Rehab of Public Marketstalls | Pub. Market at Pob. Gloria | 700000 | 8-10-18 | 12-20-18 | 72.86% | 510050
Improvement of Phantom Cave | Bgry. Malubay | 66614.9 | 8-05-18 | 12-30-18 | 78.01% | 51965
SAPAT DAPAT Proj.LGU Loan Amort. | Brgy. Maligaya | 5500000 | 1-20-18 | 12-31-18 | 92.58% | 5091990.3
Conts.of Drainage Canal (Bulaklakan) | Brgy. Bulaklakan | 1000000 | 11-15-18 | 12-31-18 | 66.14% | 661404.97
Agriculture Services
Maint. Improvement of Mangrove area | var.coastal brgys. | 75000 | 8-05-18 | 12-30-18 | 78.44% | 58830
Public Market Covered Tiangge Conts. | Mun.Public Market | 559681.92 | 10-10-18 | 12-31-18 | 10.51% | 58830
Construction of PIG PEN | Mun. Farm | 117392.04 | 9-21-18 | 12-30-18 | 99.8% | 117160
Construction of Concrete Irrigation Canal | G.Antonino,Banutan & Manguyang | 179000 | 2-27-2018 | 12-31-2018 | 99.64% | 178360.1
TOTAL |  | 22268300.97 |  |  |  | 18661719.76 |  |  |  | 840000
194941
Prepared by: |  |  |  |  | Certified correct: |  |  |  |  | 645059
1120000
#REF!
SHERALEEN C. ABUAN | [5 empty] | GERMAN D. RODEGERIO
Municipal Budget Officer | [5 empty] | Municipal Mayor