## Sheet2
FDPP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2017
Province, City or Municipality: Gloria, Oriental Mindoro
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date |  |  |  |  | 49200
Social Development | [10 empty] | 26965
126290
Renovation of Multi-Purpose Gymnasium -cum-evacuation Center | N. Jamilla Sr. Ave. | 101200 | 02-20-15 | 12-31-15 | 0 | 1267174.01 | 1 year | Various POWs | 697470.99 | 217140 | 50650
Repair and Rehabilitation of BHS (Maligaya ,Balete, Lucio Laurel, Sta. Maria, Agos, Banus & Malamig) |  | 164000 |  |  |  | 157851
Opening of Farm to Market Roads (FMR) |  | 400000 | 2015-02-16 | 2017-12-31 |  | 254350 |  |  |  | 202455 | 253105
Municipal Counterpart for BUB-Establishment of Mun.Technical-Vocational Training/Assessment/Service(TAS)Center-Component 1 (Standard Tools, Equipment &Materials for DomRAC NC II, Tansport RAC ServicingNC II and Motorcycle/small Engine Servicing NC II procured) | Maligaya | 40000 | 2016-03-09 |  |  | 695225
Conts. Of Mun. Compound & Public Market (MRF) | Various | 501905.13 | 2015-04-18 |  |  | 468925
Economic Development
Installation of Potable Water Supply System | Various Brgys | 50000 | 2017-04-18 |  |  | 49755
Fabrication of 10 units Tent |  | 285777 |  |  |  | 285777
Fabrication of 10 units Tables |  | 98410 | 2017-04-18 |  |  | 120000
Construction of Open- Typef drainage canal |  | 500000 | 2017-04-28 |  |  | 495492
Concreting of Market Road |  | 998076
Concreting of Balete Road |  | 994995 | 2017-04-07 |  |  | 994995
Construction of Standard Road Requirement Php 2M |  | 2000000 | 2017-04-28 | 2017-12-31 |  | 2000000
Construction of Municipal Oval Drainage System-Phase III |  | 1500000 | 2017-06-08 |  |  | 1497408.23
Concreting of Maligaya Road ( RB Gloria ) |  | 206929 | 2017-06-09 | 2017-12-31 |  | 199800
TOTAL |  | 7841292.13 |  |  |  | 8486752.24 |  |  | 840000
194941
Prepared by: |  |  |  |  | Certified correct: |  |  |  | 645059
186299.5
1120000
933700.5
RODOLFO S. DAPITO | [5 empty] | GERMAN D. RODEGERIO
MBO | [5 empty] | Municipal Mayor
Note on C7: Gloria: APPROPRIATION