## 3rd quarter
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE THIRD QUARTER, CY __2015__
MUNICIPALITY OF GLORIA
Program or Project | Location | Total Cost | Date Started | Target | Project Status |  | No. of | Remarks
|  |  |  | Completion | % of | Total Cost | Extensions, if
|  |  |  | Date | Completion | Incurred to Date | any
20% Development Fund -Continuing Fund(Previous Year)
Social Development
Repair and Rehabilitation of BHS (Maligaya ,Balete,
Lucio Laurel, Sta. Maria, Agos, Banus & Malamig) |  | 81685 | July 1, 2015 |  |  | 5400
Construction & Establishment of Manpower | Maligaya, Gloria
Development Center (Tech-Voc School/GSAT) | Or. Mindoro | 306800.15 | June 30, 2015 |  | 72.01% | 144350
Renovation of Multi-Purpose Gymnasium - | Maligaya, Gloria |  |  |  | waiting for
cum-evacuation Center | Or. Mindoro | 899925.99 | Sept. 1, 2015 |  | implementation | 202455
Total Social Development (Previous Year) |  | 1288411.14 |  |  |  | 352205
20% Development Fund -Continuing Fund(Current Year)
Social Development
Installation of Standard Signages for 27 Barangay
Health Station (BHSs) |  | 135000 | July 09, 2015 |  |  | 51685.5
Improvement & Rehabilitation of Controlled
Disposal Facility |  | 300000 | July 02, 2015 |  |  | 179600
Construction & Establishment of Manpower | Maligaya, Gloria |  |  |  | waiting for
Development Center (Tech-Voc School/GSAT) | Or. Mindoro | 3000000 | July 22, 2015 |  | implementation | 357578
Total Social Development |  | 3435000 |  |  |  | 588863.5
Economic Services
Sapat Dapat Project-LGU Loan Amortization to
LBP Lending Center |  | 3700000 | April 22, 2015 |  | 20% | 430090.88
Fabrication of Municipal Public Market steel | Maligaya, Gloria
Tiangge Tables | Or. Mindoro | 35000 | Sept. 16, 2015 |  |  | 23510
Assistance to Barangay for Agri-Fishery Infrastruc-
ture & Equipment -2014 Kawayanan Booth
Competition Prizes |  | 840000 | May 18, 2015 |  |  | 218714
Construction of Facilities at the Municipal Central | Maligaya, Gloria
Terminal | Or. Mindoro | 100000 | May 22, 2015 | August 2015 | 100% | 47825
Concreting of Façade of Slaughterhouse | Kawit, Gloria | 50000 | May 25, 2015 |  | 20% | 13975
Total Economic Development |  | 4725000 |  |  |  | 734114.88
General Services
Completion of Municipal Multi-Purpose Hall
a.) Acquisition of monoblock chairs | Maligaya, Gloria | 200000 | August 25, 2015 | August 25, 2015 | 100% | 192700
b.) Installation of 3-Ton Aircon Units | Or. Mindoro | 160000 | August 21, 2015 | August 21, 2015 | 100% | 144000
c.) Acquisition of Curtain Set/Blinds |  | 30000 |  |  | waiting for implementation | 3450
Electrification of Sitio Tipolo, Malamig | Malamig, Gloria | 75000 | July 27, 2015 |  | 100% | 75000
Kawayanan Festival Street Dancing Competition
Worth-of-Project Prizes |  | 1120000 | May 18, 2015 |  |  | 242043
Total General Services |  | 1585000 |  |  |  | 657193 |  |  | 2242193
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this document.
RODOLFO S. DAPITO Municipal Budget Officer
LORETO S. PEREZ Municipal Mayor