## Form 7
FDPP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE FIRST QUARTER, CY 2016
Province, City or Municipality: Gloria, Oriental Mindoro
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Renovation of Multi-Purpose Gymnasium -cum-evacuation Center | N. Jamilla Sr. Ave. | 245940 | 02-20-15 | 12-31-15 | 0 | 1010719.01 | 1 year | Various POWs
Concreting of Municipal Roads/Streets | Maligaya | 2240846.8 | 01-27-16 | 05-06-16 | 100% | 2240846.8 | none | with negative findings
Economic Development
Maintenance of Municipal Controlled Disposal Facility | Sitio Mansaring, Manguyang | 16800 | 07-02-15 |  | 65.47% | 196400
Environmental Management
Repair & Rehab of Various FMR | Kawit | 34600 | 02-07-16 |  | 23.07% | 34600
Brgy Kawit
TOTAL |  | 2538186.8 |  |  |  | 3482565.81
Prepared by: |  | Verified Status by: |  |  | Certified correct:
(SIGNED) |  | (SIGNED)
SHERALEEN C. ABUAN |  | NESTOR M. HERNANDEZ, JR. |  |  |  | LORETO S. PEREZ
Administrative Asst. II |  | Project Development Officer I |  |  |  | Municipal Mayor