## 2qtr
FDPP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE SECOND QUARTER, CY 2016
Province, City or Municipality: Gloria, Oriental Mindoro
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date |  |  |  |  | 49200
Social Development | [10 empty] | 26965
126290
Renovation of Multi-Purpose Gymnasium -cum-evacuation Center | N. Jamilla Sr. Ave. | 245940 | 02-20-15 | 12-31-15 | 0 | 1010719.01 | 1 year | Various POWs | 697470.99 | 217140 | 50650
Concreting of Municipal Roads/Streets | Maligaya | 2240846.8 | 01-27-16 | 05-06-16 | 100% | 2240846.8 | none | with negative findings |  |  | 166490
Construction of New Mun. Health Office | Maligaya | 500000 |  |  |  | 500000 |  |  |  | 202455 | 419595
Hospitals and Health Centers | Maligaya | 500000 |  |  |  | 500000
MHO #RD Yr Allocation | Maligaya | 500000 |  |  |  | 500000
KALAHI CIDDS Project | Various Brgys | 47065.22 |  |  |  | 2145000
KALAHI CIDDS Project |  | 1600000 |  |  |  | 1600000
Construction & Establishment of Manpower Development Center | Maligaya | 734967 |  |  |  | 84839.85
Economic Development
Maintenance of Municipal Controlled Disposal Facility | Sitio Mansaring, Manguyang | 16800 | 07-02-15 |  | 65.47% | 196400
Waste Disposal Facility |  | 89270 |  |  |  | 86275
Improvement & Rehab of Controlled Disposal Facility | Manguyang | 120400 |  |  |  | 16800
Rehab of Public Market Drainage System | Maligaya | 28800 |  |  |  | 228187 |  |  | 228187
Sapat Dapat Project-LGU Loan Amortization | PY | 104308.32 |  |  |  | 104308.32
Sapat Dapat Project-LGU Loan Amortization |  | 8500000 |  |  |  | 114939.1
Assistance to Brgy. Agri Fishery Infra & Equipment -2014 Kawayanan Booth Competion | Various Brgys | 20000 |  |  |  | 1120000
Kawayanan Street Dancing Competition | Various Brgys | 42000 |  |  |  | 840000
Construction of Drainage Canal at Mun. Oval | Maligaya | 899414 |  |  |  | 899414
Concreting of Municipal Roads/Streets |  | 1505646.58 |  |  |  | 2240846.8
Environmental Management
Repair & Rehab of Various FMR | Kawit | 65120 | 02-07-16 |  | 43.41% | 65120
Brgy Kawit
TOTAL |  | 17760577.92 |  |  |  | 14493695.88 |  |  | 840000
194941
Prepared by: |  | Verified Status by: |  |  | Certified correct: |  |  |  | 645059
186299.5
1120000
933700.5
SHERALEEN C. ABUAN |  | CELSO S. SEMILLA, JR. |  |  |  | LORETO S. PEREZ
Administrative Asst. II |  | MPDC |  |  |  | Municipal Mayor