## Sheet1
FDPP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE FORTH QUARTER, CY 2016
Province, City or Municipality: Gloria, Oriental Mindoro
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date |  |  |  |  | 49200
Social Development | [10 empty] | 26965
126290
Renovation of Multi-Purpose Gymnasium -cum-evacuation Center | N. Jamilla Sr. Ave. | 245940 | 02-20-15 | 12-31-15 | 0 | 1094109.01 | 1 year | Various POWs | 697470.99 | 217140 | 50650
Concreting of Municipal Roads/Streets | Maligaya | 2240846.8 | 01-27-16 | 05-06-16 | 100% | 2240846.8 | none | with negative findings |  |  | 166490
Construction of New Mun. Health Office | Maligaya | 500000 |  |  |  | 500000 |  |  |  | 202455 | 419595
Tech Voc (GIST) |  | 734967 |  |  |  | 45420
Municipal Counterpart for BUB-Establishment of Mun.Technical-Vocational Training/Assessment/Service(TAS)Center-Component 1 (Standard Tools, Equipment &Materials for DomRAC NC II, Tansport RAC ServicingNC II and Motorcycle/small Engine Servicing NC II procured) | Maligaya | 2291117.23 |  |  |  | 449811
Hospitals and Health Centers | Maligaya | 500000 |  |  |  | 500000
MHO #RD Yr Allocation | Maligaya | 500000 |  |  |  | 500000
KALAHI CIDDS Project | Various Brgys | 47065.22 |  |  |  | 2145000
KALAHI CIDDS Project |  | 1600000 |  |  |  | 1600000
Construction & Establishment of Manpower Development Center | Maligaya | 734967 |  |  |  | 84839.85
Construction of Level 1 Water System (BUB Counterpart) | Sta. Maria | 320000 |  |  |  | 320000
Construction of Level 1 Water System (BUB Counterpart) | Banus | 180000 |  |  |  | 180000
Construction of Level 1 Water System (BUB Counterpart) | Agos | 580000 |  |  |  | 580000
Construction of Level 1 Water System (BUB Counterpart) | Maligaya | 595000 |  |  |  | 595000
Construction of Level 1 Water System (BUB Counterpart) | San Antonio | 800000 |  |  |  | 800000
Expansion of Level 2Water System (BUB Counterpart) Tambong | Tambong |  |  |  |  | 225000
BUB Project Operation Timbang |  | 36450 |  |  |  | 36000
Mun.Counterpart for BUB Establishment of TecVoc-GIST |  | 1600000 |  |  |  | 23000
Economic Development
Maintenance of Municipal Controlled Disposal Facility | Sitio Mansaring, Manguyang | 16800 | 07-02-15 |  | 65.47% | 196400
Waste Disposal Facility |  | 89270 |  |  |  | 86275
Improvement & Rehab of Controlled Disposal Facility | Manguyang | 120400 |  |  |  | 16800
Rehab of Public Market Drainage System | Maligaya | 28800 |  |  |  | 228187 |  |  | 228187
Sapat Dapat Project-LGU Loan Amortization | PY | 104308.32 |  |  |  | 7149206.65
Sapat Dapat Project-LGU Loan Amortization |  | 8500000 |  |  |  | 3221226.47
Assistance to Brgy. Agri Fishery Infra & Equipment -2014 Kawayanan Booth Competion | Various Brgys | 20000 |  |  |  | 1198050
Kawayanan Street Dancing Competition | Various Brgys | 42000 |  |  |  | 840000
Construction of Drainage Canal at Mun. Oval | Maligaya | 899414 |  |  |  | 2004999.49
Concreting of Municipal Roads/Streets |  | 1505646.58 |  |  |  | 2240846.8
Environmental Management
Construction of Lighthouse |  | 58000 |  |  |  | 46790
Repair & Rehab of Various FMR | Kawit | 65120 | 02-07-16 |  | 43.41% | 65120
Brgy Kawit
Street Lighting System for Old and New Sites Php.2M |  | 3700000 |  |  |  | 112895
Fabrication Of Tent |  | 287663.13 |  |  |  | 271967.5
TOTAL |  | 24956112.15 |  |  |  | 29212928.07 |  |  | 840000
194941
Prepared by: |  |  |  |  | Certified correct: |  |  |  | 645059
186299.5
1120000
933700.5
RODOLFO S. DAPITO | [5 empty] | GERMAN D. RODEGERIO
MBO | [5 empty] | Municipal Mayor