## TFUtil~1stQtr2015
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 1ST QUARTER, CY 2015
MUNICIPAL GOVERNMENT OF GLORIA | [7 empty] | FDP Form 6 - Trust Fund Utilization
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
DOH HFIP- Health Facilities Improvement Project | Poblacion, Gloria | 750000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DOLE RO IV-B - Livelihood grant for Kawit Fish Processing | Brgy. Kawit, Gloria | 85000 | Feb. 2, 2015 | Mar 2015 | 100% | 85000 |  | Completed; submitted liquidation; waiting for Credit Notice
DSWD IV-B Baking & Decorating Cakes | 27 brgys | 50000 | Jan. 30, 2015 |  | 47.17% | 23586 |  | On-going implementation
DRRM Fund - Construction of MDRRM Operation Center | Poblacion, Gloria | 4012000 | Nov. 17, 2014 | Apr. 2015 | 77.27% | 3100059.01 |  | On-going construction
DSWD IV-B for the 2 Storey Women & Youth Livelihood & Recreational Center (BUB) | Poblacion, Gloria | 3500000 | Sep 2, 2014 | Feb. 2015 | 97.84% | 3424397.47 |  | On-going construction
DSWD IV- B Social Pension Fund (for the 1st & 2nd Quarter of 2014) | 27 brgys | 726000 | Aug. 20, 2014 | Dec. 2014 | 100% | 468000 |  | Completed; submitted liquidation; waiting for Credit Notice; balance of P258,000.00 was refunded
DILG Performance Challenge Fund - Municipal Museum cum Tourism Center | Poblacion, Gloria | 1000000 | Jul. 31, 2014 | Dec. 2014 | 100% | 1000000 |  | Completed; submitted liquidation; waiting for Credit Notice
DSWD IV-B Cellphone Repair Training | 27 brgys | 50000 | Mar 26, 2014 | Dec. 2014 | 100% | 50000 |  | Completed; submitted liquidation; waiting for Credit Notice
DSWD IV-B Livelihood on Nego Kart | 27 brgys | 500000 | April 10, 2014 | Dec. 2014 | 100% | 500000 |  | Completed; submitted liquidation; waiting for Credit Notice
DA BFAR BUB Project - Integrated Coastal Resource Management | 8 coastal brgys | 1400000 | Feb. 12, 2014 | May 2014 | 90.85% | 1271864 |  | On-going; submitted liquidation for P1,271,864.00 utilization; waiting for Credit Notice; remaining balance of P128,136.00 is subject for additional project-related procurement
OPAPP/PAMANA - Electrification of Sitios Bungkarot & Alabigan | Brgy. Buong Lupa, Gloria | 1370000 | Jun 7, 2013 | Jul. 24, 2013 | 89.21% | 1222209.58 |  | On-going; submitted liquidation of 80% (or P1.096M) downloaded fund; waiting for Credit Notice
DILG IV-B PAMANA - Opening of FTM road | Brgy. Buong Lupa, Gloria | 3000000 | May 29, 2013 | Dec. 21, 2013 | 100% | 2984913.03 |  | Completed; submitted liquidation; waiting for Credit Notice; balance of P15,086.97 was refunded
DILG IV-B PAMANA - Concreting of FTM road | Brgy. Buong Lupa, Gloria | 2500000 | Jan 23, 2013 | Apr 30, 2013 | 100% | 2483448 |  | Completed; submitted liquidation; waiting for Credit Notice; balance of P16,552.00 was refunded
OPAPP/PAMANA - Construction of Multi-Purpose Pavement | Brgy. Buong Lupa, Gloria | 150000 | Sep. 12, 2012 | Dec. 18, 2012 | 80% | 120000 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on Dec2012; waiting for Credit Notice
OPAPP/PAMANA - Construction of Day Care Center | Brgy. Buong Lupa, Gloria | 200000 | Sep. 12, 2012 | Dec. 6, 2012 | 79.73% | 159459.29 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on Dec2012; waiting for Credit Notice
OPAPP/PAMANA - Concreting of FTM Road Phase I | Brgy. Buong Lupa, Gloria | 880000 | Sep. 10, 2012 | Dec. 19, 2012 | 70.65% | 621761.01 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on May2013; waiting for Credit Notice
OPAPP/PAMANA - Purchase of Health Equipment | Brgy. Buong Lupa, Gloria | 50000 | Jul 23, 2012 | Dec. 18, 2012 | 100% | 49204.32 |  | Completed; re-submitted liquidation after getting audit suggestion on 1st submission on Dec.2012; waiting for Credit Notice
OPAPP/PAMANA - Abaca Production & Development | Brgy. Buong Lupa, Gloria | 280000 | Jul 23, 2012 | May 20, 2013 | 100% | 278923.79 |  | Completed; re-submitted liquidation after getting audit suggestion on 1st submission on Dec.2012; waiting for Credit Notice
CHD IV-B Construction of TB DOTS Building | Poblacion, Gloria | 200000 | July 21, 2012 | Dec 2014 | 100% | 200000 |  | Completed; submitted liquidation; waiting for Credit Notice
DOH Facilities Enhancement Program (Water System) | Brgy. Buong Lupa, Gloria | 431780 | Dec. 2011 | Oct 2012 | 100% | 391710 |  | Completed; submitted liquidation; waiting for Credit Notice; balance of P40,070.00 was refunded
DSWD IV-B Supplemental Feeding Program | 27 brgys | 1832025 | Oct. 2011 | Oct 2012 | 100% | 1769483.28 |  | Completed; submitted liquidation; waiting for Credit Notice; balance of P62,541.72 was refunded
DA IV-B Bagsakan Center | Public Market, Poblacion | 860000 | Oct. 2010 | Dec. 2012 | 100% | 830500.15 |  | Completed; submitted liquidation; waiting for Credit Notice; balance of P29,499.15 was refunded
DA IV-B Farm to Market Road Rehabilitation | Brgys. Maragooc-Agsalin | 9964508.28 | Apr. 2010 | Dec. 2010 | 100% | 9964508.28 |  | Completed; submitted liquidation; P53,528.57 was recouped or refunded from contractor based on Credit Notice; notice of refund was sent to COA for consideration
DA IV-B Farm to Market Road Rehabilitation | Brgys. Agos-Malamig | 9906611.19 | Apr. 2010 | Dec. 2010 | 100% | 9906611.19 |  | Completed; submitted liquidation; P42,869.93 was recouped or refunded from contractor based on Credit Notice; notice of refund was sent to COA for consideration
DA IV-B Farm to Market Road Rehabilitation | Brgys. Maligaya-Agos | 9942118.52 | Apr. 2010 | Dec. 2010 | 100% | 9942118.52 |  | Completed; submitted liquidation; P31,910.72 was recouped or refunded from contractor based on Credit Notice; notice of refund was sent to COA for consideration
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
RODERICK B. LOGDAT | [5 empty] | LORETO S. PEREZ
Municipal Accountant | [5 empty] | Municipal Mayor