## TFUtil~3rdQtr2015
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 3RD QUARTER, CY 2015
MUNICIPAL GOVERNMENT OF GLORIA | [7 empty] | FDP Form 6 - Trust Fund Utilization
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Narra, Gloria | 520000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Sta. Maria, Gloria | 750000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DILG Region IVB - 2015 BUB Water Fund for Consruction of Water System Level I | Brgy. Banus, Gloria | 500000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DILG Region IVB - 1st tranche 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. Maligaya, Gloria | 1644000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DILG Region IVB - 1st tranche 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. San Antonio, Gloria | 1600000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DILG Region IVB - 1st tranche 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. Agos, Gloria | 1600000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DILG Region IVB - 2015 BUB Water Fund for Extension of Water System Level II | Brgy. Tambong, Gloria | 775000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DILG Region IVB - 1st Tranche of 2014 GPBP Fund for road opening | Brgy. Malubay, Gloria | 360000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DILG Region IVB - 1st Tranche of 2014 GPBP Fund for road opening | Brgy. Alma Villa, Gloria | 1080000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DSWD IV - B Orientation & Planning Workshop on Child & Youth Welfare under GPB | Poblacion, Gloria | 170000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DOH HFIP- Health Facilities Improvement Project | Poblacion, Gloria | 1350000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DSWD IV- B Social Pension Fund (for the 3rd & 4th Quarter of 2014, w/ addtl in 1st & 2nd Qtr) | 27 brgys | 2844000 | May 30, 2015 | June 2015 | 100% | 2725500 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV- B Social Pension Fund | 27 brgys | 284000 | Sept. 30, 2015 |  | 0% | 0 |  | Recently received fund; for release to Senior Citizen
DOLE RO IV-B - Livelihood grant for Kawit Fish Processing | Brgy. Kawit, Gloria | 85000 | Feb. 2, 2015 | Mar 2015 | 100% | 85000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV-B Baking & Decorating Cakes | 27 brgys | 50000 | Jan. 30, 2015 | May 28, 2015 | 100% | 50000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DRRM Fund - Construction of MDRRM Operation Center | Poblacion, Gloria | 4012000 | Nov. 17, 2014 | Apr. 2015 | 100% | 4007103.25 |  | Completed construction of building
DSWD IV-B for the 2 Storey Women & Youth Livelihood & Recreational Center (BUB) | Poblacion, Gloria | 3500000 | Sep 2, 2014 | Feb. 2015 | 100% | 3499898.47 |  | Completed; for submission of liquidation to COA
DSWD IV- B Social Pension Fund (for the 1st & 2nd Quarter of 2014) | 27 brgys | 726000 | Aug. 20, 2014 | Dec. 2014 | 100% | 468000 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P258,000.00 was refunded to DSWD
DILG Performance Challenge Fund - Municipal Museum cum Tourism Center | Poblacion, Gloria | 1000000 | Jul. 31, 2014 | Dec. 2014 | 100% | 1000000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA | 23
DSWD IV-B Cellphone Repair Training | 27 brgys | 50000 | Mar 26, 2014 | Dec. 2014 | 100% | 50000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV-B Livelihood on Nego Kart | 27 brgys | 500000 | April 10, 2014 | Dec. 2014 | 100% | 500000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA BFAR BUB Project - Integrated Coastal Resource Management | 8 coastal brgys | 1400000 | Feb. 12, 2014 | May 2014 | 100% | 1400000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
OPAPP/PAMANA - Electrification of Sitios Bungkarot & Alabigan | Brgy. Buong Lupa, Gloria | 1370000 | Jun 7, 2013 | Jul. 24, 2013 | 89.21% | 1222209.58 |  | On-going; submitted liquidation of 80% (or P1.096M) downloaded fund & waiting for Credit Notice from COA
DILG IV-B PAMANA - Opening of FTM road | Brgy. Buong Lupa, Gloria | 3000000 | May 29, 2013 | Dec. 21, 2013 | 100% | 2984913.03 |  | Completed; submitted liquidation for the P600,000 final funding & waiting for Credit Notice from COA; balance of P15,086.97 was refunded to DILG
DILG IV-B PAMANA - Concreting of FTM road | Brgy. Buong Lupa, Gloria | 2500000 | Jan 23, 2013 | Apr 30, 2013 | 100% | 2483448 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P16,552.00 was refunded to DILG
OPAPP/PAMANA - Construction of Multi-Purpose Pavement | Brgy. Buong Lupa, Gloria | 150000 | Sep. 12, 2012 | Dec. 18, 2012 | 80% | 120000 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on Dec2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Construction of Day Care Center | Brgy. Buong Lupa, Gloria | 200000 | Sep. 12, 2012 | Dec. 6, 2012 | 79.73% | 159459.29 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on Dec2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Concreting of FTM Road Phase I | Brgy. Buong Lupa, Gloria | 880000 | Sep. 10, 2012 | Dec. 19, 2012 | 70.65% | 621761.01 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on May2013 & waiting for Credit Notice from COA
OPAPP/PAMANA - Purchase of Health Equipment | Brgy. Buong Lupa, Gloria | 50000 | Jul 23, 2012 | Dec. 18, 2012 | 100% | 49204.32 |  | Completed; re-submitted liquidation after getting audit suggestion on 1st submission on Dec.2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Abaca Production & Development | Brgy. Buong Lupa, Gloria | 280000 | Jul 23, 2012 | May 20, 2013 | 100% | 278923.79 |  | Completed; re-submitted liquidation after getting audit suggestion on 1st submission on Dec.2012 & waiting for Credit Notice from COA
CHD IV-B Construction of TB DOTS Building | Poblacion, Gloria | 200000 | July 21, 2012 | Dec 2014 | 100% | 200000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DOH Facilities Enhancement Program (Water System) | Brgy. Buong Lupa, Gloria | 431780 | Dec. 2011 | Oct 2012 | 100% | 391710 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P40,070.00 was refunded to DOH
DSWD IV-B Supplemental Feeding Program | 27 brgys | 1832025 | Oct. 2011 | Oct 2012 | 100% | 1769483.28 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P62,541.72 was refunded to DSWD
DA IV-B Bagsakan Center | Public Market, Poblacion | 860000 | Oct. 2010 | Dec. 2012 | 100% | 830500.15 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P29,499.15 was refunded to DA-ORMAES
DA IV-B Farm to Market Road Rehabilitation | Brgys. Maragooc-Agsalin | 9964508.28 | Apr. 2010 | Dec. 2010 | 100% | 9964508.28 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA IV-B Farm to Market Road Rehabilitation | Brgys. Agos-Malamig | 9906611.19 | Apr. 2010 | Dec. 2010 | 100% | 9906611.19 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA IV-B Farm to Market Road Rehabilitation | Brgys. Maligaya-Agos | 9942118.52 | Apr. 2010 | Dec. 2010 | 100% | 9942118.52 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
RODERICK B. LOGDAT | [5 empty] | LORETO S. PEREZ
Municipal Accountant | [5 empty] | Municipal Mayor