## TFUtil~3rdQtr2015
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 3RD QUARTER, CY 2015
MUNICIPAL GOVERNMENT OF GLORIA | [7 empty] | FDP Form 6 - Trust Fund Utilization
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Narra, Gloria | 520000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Sta. Maria, Gloria | 750000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DILG Region IVB - 2015 BUB Water Fund for Consruction of Water System Level I | Brgy. Banus, Gloria | 500000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DILG Region IVB - 1st tranche 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. Maligaya, Gloria | 1644000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DILG Region IVB - 1st tranche 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. San Antonio, Gloria | 1600000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DILG Region IVB - 1st tranche 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. Agos, Gloria | 1600000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DILG Region IVB - 2015 BUB Water Fund for Extension of Water System Level II | Brgy. Tambong, Gloria | 775000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DILG Region IVB - 1st Tranche of 2014 GPBP Fund for road opening | Brgy. Malubay, Gloria | 360000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DILG Region IVB - 1st Tranche of 2014 GPBP Fund for road opening | Brgy. Alma Villa, Gloria | 1080000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DSWD IV - B Orientation & Planning Workshop on Child & Youth Welfare under GPB | Poblacion, Gloria | 170000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DOH HFIP- Health Facilities Improvement Project | Poblacion, Gloria | 1350000 | not yet |  | 0% | 0 |  | For Implementation CY 2015
DSWD IV- B Social Pension Fund (for the 3rd & 4th Quarter of 2014, w/ addtl in 1st & 2nd Qtr) | 27 brgys | 2844000 | May 30, 2015 | June 2015 | 100% | 2725500 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV- B Social Pension Fund | 27 brgys | 284000 | Sept. 30, 2015 |  | 0% | 0 |  | Recently received fund; for release to Senior Citizen
DOLE RO IV-B - Livelihood grant for Kawit Fish Processing | Brgy. Kawit, Gloria | 85000 | Feb. 2, 2015 | Mar 2015 | 100% | 85000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV-B Baking & Decorating Cakes | 27 brgys | 50000 | Jan. 30, 2015 | May 28, 2015 | 100% | 50000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DRRM Fund - Construction of MDRRM Operation Center | Poblacion, Gloria | 4012000 | Nov. 17, 2014 | Apr. 2015 | 100% | 4007103.25 |  | Completed construction of building
DSWD IV-B for the 2 Storey Women & Youth Livelihood & Recreational Center (BUB) | Poblacion, Gloria | 3500000 | Sep 2, 2014 | Feb. 2015 | 100% | 3499898.47 |  | Completed; for submission of liquidation to COA
DSWD IV- B Social Pension Fund (for the 1st & 2nd Quarter of 2014) | 27 brgys | 726000 | Aug. 20, 2014 | Dec. 2014 | 100% | 468000 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P258,000.00 was refunded to DSWD
DILG Performance Challenge Fund - Municipal Museum cum Tourism Center | Poblacion, Gloria | 1000000 | Jul. 31, 2014 | Dec. 2014 | 100% | 1000000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA | 23
DSWD IV-B Cellphone Repair Training | 27 brgys | 50000 | Mar 26, 2014 | Dec. 2014 | 100% | 50000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV-B Livelihood on Nego Kart | 27 brgys | 500000 | April 10, 2014 | Dec. 2014 | 100% | 500000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA BFAR BUB Project - Integrated Coastal Resource Management | 8 coastal brgys | 1400000 | Feb. 12, 2014 | May 2014 | 100% | 1400000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
OPAPP/PAMANA - Electrification of Sitios Bungkarot & Alabigan | Brgy. Buong Lupa, Gloria | 1370000 | Jun 7, 2013 | Jul. 24, 2013 | 89.21% | 1222209.58 |  | On-going; submitted liquidation of 80% (or P1.096M) downloaded fund & waiting for Credit Notice from COA
DILG IV-B PAMANA - Opening of FTM road | Brgy. Buong Lupa, Gloria | 3000000 | May 29, 2013 | Dec. 21, 2013 | 100% | 2984913.03 |  | Completed; submitted liquidation for the P600,000 final funding & waiting for Credit Notice from COA; balance of P15,086.97 was refunded to DILG
DILG IV-B PAMANA - Concreting of FTM road | Brgy. Buong Lupa, Gloria | 2500000 | Jan 23, 2013 | Apr 30, 2013 | 100% | 2483448 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P16,552.00 was refunded to DILG
OPAPP/PAMANA - Construction of Multi-Purpose Pavement | Brgy. Buong Lupa, Gloria | 150000 | Sep. 12, 2012 | Dec. 18, 2012 | 80% | 120000 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on Dec2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Construction of Day Care Center | Brgy. Buong Lupa, Gloria | 200000 | Sep. 12, 2012 | Dec. 6, 2012 | 79.73% | 159459.29 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on Dec2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Concreting of FTM Road Phase I | Brgy. Buong Lupa, Gloria | 880000 | Sep. 10, 2012 | Dec. 19, 2012 | 70.65% | 621761.01 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on May2013 & waiting for Credit Notice from COA
OPAPP/PAMANA - Purchase of Health Equipment | Brgy. Buong Lupa, Gloria | 50000 | Jul 23, 2012 | Dec. 18, 2012 | 100% | 49204.32 |  | Completed; re-submitted liquidation after getting audit suggestion on 1st submission on Dec.2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Abaca Production & Development | Brgy. Buong Lupa, Gloria | 280000 | Jul 23, 2012 | May 20, 2013 | 100% | 278923.79 |  | Completed; re-submitted liquidation after getting audit suggestion on 1st submission on Dec.2012 & waiting for Credit Notice from COA
CHD IV-B Construction of TB DOTS Building | Poblacion, Gloria | 200000 | July 21, 2012 | Dec 2014 | 100% | 200000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DOH Facilities Enhancement Program (Water System) | Brgy. Buong Lupa, Gloria | 431780 | Dec. 2011 | Oct 2012 | 100% | 391710 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P40,070.00 was refunded to DOH
DSWD IV-B Supplemental Feeding Program | 27 brgys | 1832025 | Oct. 2011 | Oct 2012 | 100% | 1769483.28 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P62,541.72 was refunded to DSWD
DA IV-B Bagsakan Center | Public Market, Poblacion | 860000 | Oct. 2010 | Dec. 2012 | 100% | 830500.15 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P29,499.15 was refunded to DA-ORMAES
DA IV-B Farm to Market Road Rehabilitation | Brgys. Maragooc-Agsalin | 9964508.28 | Apr. 2010 | Dec. 2010 | 100% | 9964508.28 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA IV-B Farm to Market Road Rehabilitation | Brgys. Agos-Malamig | 9906611.19 | Apr. 2010 | Dec. 2010 | 100% | 9906611.19 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA IV-B Farm to Market Road Rehabilitation | Brgys. Maligaya-Agos | 9942118.52 | Apr. 2010 | Dec. 2010 | 100% | 9942118.52 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
RODERICK B. LOGDAT | [5 empty] | LORETO S. PEREZ
Municipal Accountant | [5 empty] | Municipal Mayor

## TFUtil~4thQtr2015
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 4TH QUARTER, CY 2015
MUNICIPAL GOVERNMENT OF GLORIA | [7 empty] | FDP Form 6 - Trust Fund Utilization
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
DILG Region IVB - 2015 Salintubig Fund (Construction of Potable Water Supply) | Brgy. Guimbonan, Gloria | 2000000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 2015 Salintubig Fund (Construction of Potable Water Supply) | Brgy. Maragooc, Gloria | 2000000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 2015 Salintubig Fund (Construction of Potable Water Supply) | Brgy. Mirayan, Gloria | 1000000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Narra, Gloria | 520000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Sta. Maria, Gloria | 750000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Banus, Gloria | 500000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 1st tranche 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. Maligaya, Gloria | 1644000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 1st tranche 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. San Antonio, Gloria | 1600000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 1st tranche 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. Agos, Gloria | 1600000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 2015 BUB Water Fund for Extension of Water System Level II | Brgy. Tambong, Gloria | 775000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 1st Tranche of 2014 GPBP Fund for road opening | Brgy. Malubay, Gloria | 360000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 1st Tranche of 2014 GPBP Fund for road opening | Brgy. Alma Villa, Gloria | 1080000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DSWD IV - B Orientation & Planning Workshop on Child & Youth Welfare under GPB | Poblacion, Gloria | 170000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DOH HFIP- Health Facilities Improvement Project | Poblacion, Gloria | 1350000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DSWD IV- B Social Pension Fund (for the 3rd & 4th Quarter of 2014, w/ addtl in 1st & 2nd Qtr) | 27 brgys | 2844000 | May 30, 2015 | June 2015 | 100% | 2725500 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV- B Social Pension Fund | 27 brgys | 258000 | Sept. 30, 2015 | Oct 2015 | 100% | 244500 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P13,500.00 was refunded to DSWD
DSWD IV- B Social Pension Fund (1st - 4th Quarter 2015) | 27 brgys | 6162000 | Oct. 21, 2015 | Nov. 20, 2015 | 100% | 5759000 | 403000 | Completed; submitted liquidation to COA; waiting for Credit Notice; out of P403,000 remaining balance, P378,500.00 was refunded to DSWD; P24,500 remains to be processed
DOLE RO IV-B - Livelihood grant for Kawit Fish Processing | Brgy. Kawit, Gloria | 85000 | Feb. 2, 2015 | Mar 2015 | 100% | 85000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV-B Baking & Decorating Cakes | 27 brgys | 50000 | Jan. 30, 2015 | May 28, 2015 | 100% | 50000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DRRM Fund - Construction of MDRRM Operation Center | Poblacion, Gloria | 4012000 | Nov. 17, 2014 | Apr. 2015 | 100% | 4007103.25 |  | Completed construction of building
DSWD IV-B for the 2 Storey Women & Youth Livelihood & Recreational Center (BUB) | Poblacion, Gloria | 3500000 | Sep 2, 2014 | Feb. 2015 | 100% | 3499898.47 |  | Completed; for submission of liquidation to COA
DSWD IV- B Social Pension Fund (for the 1st & 2nd Quarter of 2014) | 27 brgys | 726000 | Aug. 20, 2014 | Dec. 2014 | 100% | 468000 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P258,000.00 was refunded to DSWD
DILG Performance Challenge Fund - Municipal Museum cum Tourism Center | Poblacion, Gloria | 1000000 | Jul. 31, 2014 | Dec. 2014 | 100% | 1000000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA | 23
DSWD IV-B Cellphone Repair Training | 27 brgys | 50000 | Mar 26, 2014 | Dec. 2014 | 100% | 50000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV-B Livelihood on Nego Kart | 27 brgys | 500000 | April 10, 2014 | Dec. 2014 | 100% | 500000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA BFAR BUB Project - Integrated Coastal Resource Management | 8 coastal brgys | 1400000 | Feb. 12, 2014 | May 2014 | 100% | 1400000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
OPAPP/PAMANA - Electrification of Sitios Bungkarot & Alabigan | Brgy. Buong Lupa, Gloria | 1370000 | Jun 7, 2013 | Jul. 24, 2013 | 89.21% | 1222209.58 |  | On-going; submitted liquidation of 80% (or P1.096M) downloaded fund & waiting for Credit Notice from COA
DILG IV-B PAMANA - Opening of FTM road | Brgy. Buong Lupa, Gloria | 3000000 | May 29, 2013 | Dec. 21, 2013 | 100% | 2984913.03 |  | Completed; submitted liquidation for the P600,000 final funding & waiting for Credit Notice from COA; balance of P15,086.97 was refunded to DILG
DILG IV-B PAMANA - Concreting of FTM road | Brgy. Buong Lupa, Gloria | 2500000 | Jan 23, 2013 | Apr 30, 2013 | 100% | 2483448 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P16,552.00 was refunded to DILG
OPAPP/PAMANA - Construction of Multi-Purpose Pavement | Brgy. Buong Lupa, Gloria | 150000 | Sep. 12, 2012 | Dec. 18, 2012 | 80% | 120000 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on Dec2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Construction of Day Care Center | Brgy. Buong Lupa, Gloria | 200000 | Sep. 12, 2012 | Dec. 6, 2012 | 79.73% | 159459.29 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on Dec2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Concreting of FTM Road Phase I | Brgy. Buong Lupa, Gloria | 880000 | Sep. 10, 2012 | Dec. 19, 2012 | 70.65% | 621761.01 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on May2013 & waiting for Credit Notice from COA
OPAPP/PAMANA - Purchase of Health Equipment | Brgy. Buong Lupa, Gloria | 50000 | Jul 23, 2012 | Dec. 18, 2012 | 100% | 49204.32 |  | Completed; re-submitted liquidation after getting audit suggestion on 1st submission on Dec.2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Abaca Production & Development | Brgy. Buong Lupa, Gloria | 280000 | Jul 23, 2012 | May 20, 2013 | 100% | 278923.79 |  | Completed; re-submitted liquidation after getting audit suggestion on 1st submission on Dec.2012 & waiting for Credit Notice from COA
CHD IV-B Construction of TB DOTS Building | Poblacion, Gloria | 200000 | July 21, 2012 | Dec 2014 | 100% | 200000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DOH Facilities Enhancement Program (Water System) | Brgy. Buong Lupa, Gloria | 431780 | Dec. 2011 | Oct 2012 | 100% | 391710 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P40,070.00 was refunded to DOH
DSWD IV-B Supplemental Feeding Program | 27 brgys | 1832025 | Oct. 2011 | Oct 2012 | 100% | 1769483.28 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P62,541.72 was refunded to DSWD
DA IV-B Bagsakan Center | Public Market, Poblacion | 860000 | Oct. 2010 | Dec. 2012 | 100% | 830500.15 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P29,499.15 was refunded to DA-ORMAES
DA IV-B Farm to Market Road Rehabilitation | Brgys. Maragooc-Agsalin | 9964508.28 | Apr. 2010 | Dec. 2010 | 100% | 9964508.28 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA IV-B Farm to Market Road Rehabilitation | Brgys. Agos-Malamig | 9906611.19 | Apr. 2010 | Dec. 2010 | 100% | 9906611.19 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA IV-B Farm to Market Road Rehabilitation | Brgys. Maligaya-Agos | 9942118.52 | Apr. 2010 | Dec. 2010 | 100% | 9942118.52 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
RODERICK B. LOGDAT | [5 empty] | LORETO S. PEREZ
Municipal Accountant | [5 empty] | Municipal Mayor

## TFUtil~1stQtr2016
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 1ST QUARTER, CY 2016
MUNICIPAL GOVERNMENT OF GLORIA | [7 empty] | FDP Form 6 - Trust Fund Utilization
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
DILG Region IVB - 2015 Salintubig Fund (Construction of Potable Water Supply) | Brgy. Guimbonan, Gloria | 2000000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 2015 Salintubig Fund (Construction of Potable Water Supply) | Brgy. Maragooc, Gloria | 2000000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 2015 Salintubig Fund (Construction of Potable Water Supply) | Brgy. Mirayan, Gloria | 1000000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Narra, Gloria | 520000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Sta. Maria, Gloria | 750000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Banus, Gloria | 500000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 1st tranche 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. Maligaya, Gloria | 1644000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 1st tranche 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. San Antonio, Gloria | 1600000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 1st tranche 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. Agos, Gloria | 1600000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 2015 BUB Water Fund for Extension of Water System Level II | Brgy. Tambong, Gloria | 775000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 1st Tranche of 2014 GPBP Fund for road opening | Brgy. Malubay, Gloria | 360000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DILG Region IVB - 1st Tranche of 2014 GPBP Fund for road opening | Brgy. Alma Villa, Gloria | 1080000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DSWD IV - B Orientation & Planning Workshop on Child & Youth Welfare under GPB | Poblacion, Gloria | 170000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DOH HFIP- Health Facilities Improvement Project | Poblacion, Gloria | 1350000 | not yet |  | 0% | 0 |  | For Implementation CY 2016
DSWD IV- B Social Pension Fund (for the 3rd & 4th Quarter of 2014, w/ addtl in 1st & 2nd Qtr) | 27 brgys | 2844000 | May 30, 2015 | June 2015 | 100% | 2725500 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV- B Social Pension Fund | 27 brgys | 258000 | Sept. 30, 2015 | Oct 2015 | 100% | 244500 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P13,500.00 was refunded to DSWD
DSWD IV- B Social Pension Fund (1st - 4th Quarter 2015) | 27 brgys | 6162000 | Oct. 21, 2015 | Nov. 20, 2015 | 100% | 5759000 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; out of P403,000 remaining balance, P378,500.00 was refunded to DSWD; P24,500 remains to be processed
DOLE RO IV-B - Livelihood grant for Kawit Fish Processing | Brgy. Kawit, Gloria | 85000 | Feb. 2, 2015 | Mar 2015 | 100% | 85000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV-B Baking & Decorating Cakes | 27 brgys | 50000 | Jan. 30, 2015 | May 28, 2015 | 100% | 50000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DRRM Fund - Construction of MDRRM Operation Center | Poblacion, Gloria | 4012000 | Nov. 17, 2014 | Apr. 2015 | 100% | 4007103.25 |  | Completed construction of building
DSWD IV-B for the 2 Storey Women & Youth Livelihood & Recreational Center (BUB) | Poblacion, Gloria | 3500000 | Sep 2, 2014 | Feb. 2015 | 100% | 3499898.47 |  | Completed; for submission of liquidation to COA
DSWD IV- B Social Pension Fund (for the 1st & 2nd Quarter of 2014) | 27 brgys | 726000 | Aug. 20, 2014 | Dec. 2014 | 100% | 468000 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P258,000.00 was refunded to DSWD
DILG Performance Challenge Fund - Municipal Museum cum Tourism Center | Poblacion, Gloria | 1000000 | Jul. 31, 2014 | Dec. 2014 | 100% | 1000000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA | 23
DSWD IV-B Cellphone Repair Training | 27 brgys | 50000 | Mar 26, 2014 | Dec. 2014 | 100% | 50000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV-B Livelihood on Nego Kart | 27 brgys | 500000 | April 10, 2014 | Dec. 2014 | 100% | 500000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA BFAR BUB Project - Integrated Coastal Resource Management | 8 coastal brgys | 1400000 | Feb. 12, 2014 | May 2014 | 100% | 1400000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
OPAPP/PAMANA - Electrification of Sitios Bungkarot & Alabigan | Brgy. Buong Lupa, Gloria | 1370000 | Jun 7, 2013 | Jul. 24, 2013 | 89.21% | 1222209.58 |  | On-going; submitted liquidation of 80% (or P1.096M) downloaded fund & waiting for Credit Notice from COA
DILG IV-B PAMANA - Opening of FTM road | Brgy. Buong Lupa, Gloria | 3000000 | May 29, 2013 | Dec. 21, 2013 | 100% | 2984913.03 |  | Completed; submitted liquidation for the P600,000 final funding & waiting for Credit Notice from COA; balance of P15,086.97 was refunded to DILG
DILG IV-B PAMANA - Concreting of FTM road | Brgy. Buong Lupa, Gloria | 2500000 | Jan 23, 2013 | Apr 30, 2013 | 100% | 2483448 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P16,552.00 was refunded to DILG
OPAPP/PAMANA - Construction of Multi-Purpose Pavement | Brgy. Buong Lupa, Gloria | 150000 | Sep. 12, 2012 | Dec. 18, 2012 | 80% | 120000 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on Dec2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Construction of Day Care Center | Brgy. Buong Lupa, Gloria | 200000 | Sep. 12, 2012 | Dec. 6, 2012 | 79.73% | 159459.29 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on Dec2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Concreting of FTM Road Phase I | Brgy. Buong Lupa, Gloria | 880000 | Sep. 10, 2012 | Dec. 19, 2012 | 70.65% | 621761.01 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on May2013 & waiting for Credit Notice from COA
OPAPP/PAMANA - Purchase of Health Equipment | Brgy. Buong Lupa, Gloria | 50000 | Jul 23, 2012 | Dec. 18, 2012 | 100% | 49204.32 |  | Completed; re-submitted liquidation after getting audit suggestion on 1st submission on Dec.2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Abaca Production & Development | Brgy. Buong Lupa, Gloria | 280000 | Jul 23, 2012 | May 20, 2013 | 100% | 278923.79 |  | Completed; re-submitted liquidation after getting audit suggestion on 1st submission on Dec.2012 & waiting for Credit Notice from COA
CHD IV-B Construction of TB DOTS Building | Poblacion, Gloria | 200000 | July 21, 2012 | Dec 2014 | 100% | 200000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DOH Facilities Enhancement Program (Water System) | Brgy. Buong Lupa, Gloria | 431780 | Dec. 2011 | Oct 2012 | 100% | 391710 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P40,070.00 was refunded to DOH
DSWD IV-B Supplemental Feeding Program | 27 brgys | 1832025 | Oct. 2011 | Oct 2012 | 100% | 1769483.28 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P62,541.72 was refunded to DSWD
DA IV-B Bagsakan Center | Public Market, Poblacion | 860000 | Oct. 2010 | Dec. 2012 | 100% | 830500.15 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P29,499.15 was refunded to DA-ORMAES
DA IV-B Farm to Market Road Rehabilitation | Brgys. Maragooc-Agsalin | 9964508.28 | Apr. 2010 | Dec. 2010 | 100% | 9964508.28 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA IV-B Farm to Market Road Rehabilitation | Brgys. Agos-Malamig | 9906611.19 | Apr. 2010 | Dec. 2010 | 100% | 9906611.19 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA IV-B Farm to Market Road Rehabilitation | Brgys. Maligaya-Agos | 9942118.52 | Apr. 2010 | Dec. 2010 | 100% | 9942118.52 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
RODERICK B. LOGDAT | [5 empty] | LORETO S. PEREZ
Municipal Accountant | [5 empty] | Municipal Mayor

## TFUtil~2ndQtr2016
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 2ND QUARTER, CY 2016
MUNICIPAL GOVERNMENT OF GLORIA | [7 empty] | FDP Form 6 - Trust Fund Utilization
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
DA Integrated Community Food Production 2016 |  | 5000000 | July 2016 |  |  |  |  | For Implementation in CY2016
DA BUB Project - Irrigation Small Water Impounding Project |  | 270000 | July 2016 |  |  |  |  | For Implementation in CY2016
DILG Region IVB - 2015 Salintubig Fund (Construction of Potable Water Supply) | Brgy. Guimbonan, Gloria | 2000000 | Apr 29, 2016 |  | 43.13% | 862522.79 |  | Construction in progress
DILG Region IVB - 2015 Salintubig Fund (Construction of Potable Water Supply) | Brgy. Maragooc, Gloria | 2000000 | May 24, 2016 |  | 18.34% | 366851.48 |  | Construction in progress
DILG Region IVB - 2015 Salintubig Fund (Construction of Potable Water Supply) | Brgy. Mirayan, Gloria | 1000000 | May 31, 2016 |  | 62.01% | 620113.89 |  | Construction in progress
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Narra, Gloria | 500000 | Apr 29, 2016 |  | 83.4% | 416998.02 |  | Construction in progress
DILG Region IVB - 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. San Antonio, Gloria | 2800000 | Apr 26, 2016 |  | 63.3% | 1772535.99 |  | Construction in progress; 1st tranche P1.6M was liquidated; with P800,000 LGU counterpart
DILG Region IVB - 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. Maligaya, Gloria | 2655000 | March 31, 2016 |  | 75.76% | 2011334.46 |  | Construction in progress; 1st tranche P1.644M was liquidated; with P595,000 LGU counterpart
DILG Region IVB - 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. Agos, Gloria | 2580000 | March 31, 2016 |  | 67.58% | 1743611.84 |  | Construction in progress; 1st tranche P1.6M was liquidated; with P580,000 LGU counterpart
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Sta. Maria, Gloria | 1070000 | Apr 26, 2016 |  | 83.01% | 888181.9 |  | Construction in progress; with P320,000 LGU counterpart
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Banus, Gloria | 700000 | March 31, 2016 |  | 55.87% | 391115.5 |  | Construction in progress; with P180,000 LGU counterpart
DILG Region IVB - 2015 BUB Water Fund for Extension of Water System Level II | Brgy. Tambong, Gloria | 1000000 | Apr 29, 2016 |  | 35.93% | 359279.99 |  | Construction in progress; with P225,000 LGU counterpart
DILG Region IVB - 2014 GPBP Fund for road opening | Brgy. Malubay, Gloria | 450000 | Feb 29, 2016 | Apr 29, 2016 | 100% | 366258.6 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P83,741.40 was refunded to DILG
DILG Region IVB - 2014 GPBP Fund for road opening | Brgy. Alma Villa, Gloria | 1350000 | Feb 29, 2016 | Apr 29, 2016 | 100% | 1202719.6 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P147,280.40 was refunded to DILG
DSWD IV - B Construction of Day Care Centers | Brgy. M. Adriatico | 600000 | March 31, 2016 | Sept 2016 | 97.55% | 585326 |  | Construction in progress; 1st tranche subject for liquidation
DSWD IV - B Construction of Day Care Centers | Brgy. Manguyang | 600000 | March 31, 2016 | Sept 2016 | 95.69% | 574148 |  | Construction in progress; 1st tranche subject for liquidation
DSWD IV - B Construction of Day Care Centers | Brgy. Malayong | 640000 | Apr 26, 2016 | Sept 2016 | 80.2% | 513281.93 |  | Construction in progress; 1st tranche subject for liquidation
DSWD IV - B Construction of Day Care Centers | Brgy. Mirayan | 640000 | March 21, 2016 | Sept 2016 | 82.46% | 527772 |  | Construction in progress; 1st tranche subject for liquidation
DSWD IV- B Fund for Women Welfare Program under (GPB) | Poblacion, Gloria | 85000 | March 31, 2016 | April 26, 2016 | 100% | 85000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV - B Orientation & Planning Workshop on Child & Youth Welfare under GPB | Poblacion, Gloria | 85000 | May 24, 2016 | May 31, 2016 | 100% | 85000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DOH HFIP- Health Facilities Improvement Project | Poblacion, Gloria | 3000000 | March 31, 2016 | June 2016 | 100% | 2443268.88 |  | Physical accomplishment 100% completed; waiting for final billing
DSWD IV- B Social Pension Fund (for the 2nd Quarter 2016, w/ addtl Jan-Jun 2016) | 27 brgys | 2740500 | June 30, 2016 | July 2016 | 100% | 2740500 |  | Completed; in process of liquidation
DSWD IV- B Social Pension Fund (for the 1st Quarter 2016) | 27 brgys | 1540500 | March 31, 2016 | April 25, 2016 | 100% | 1369500 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV- B Social Pension Fund (1st - 4th Quarter 2015) | 27 brgys | 6162000 | Oct. 21, 2015 | Nov. 20, 2015 | 100% | 5759000 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P403,000 was refunded to DSWD
DSWD IV- B Social Pension Fund | 27 brgys | 258000 | Sept. 30, 2015 | Oct 2015 | 100% | 244500 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P13,500.00 was refunded to DSWD
DSWD IV- B Social Pension Fund (for the 3rd & 4th Quarter of 2014, w/ addtl in 1st & 2nd Qtr) | 27 brgys | 2844000 | May 30, 2015 | June 2015 | 100% | 2725500 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DOLE RO IV-B - Livelihood grant for Kawit Fish Processing | Brgy. Kawit, Gloria | 85000 | Feb. 2, 2015 | Mar 2015 | 100% | 85000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV-B Baking & Decorating Cakes | 27 brgys | 50000 | Jan. 30, 2015 | May 28, 2015 | 100% | 50000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DRRM Fund - Construction of MDRRM Operation Center | Poblacion, Gloria | 4012000 | Nov. 17, 2014 | Apr. 2015 | 100% | 4007103.25 |  | Completed construction of building
DSWD IV-B for the 2 Storey Women & Youth Livelihood & Recreational Center (BUB) | Poblacion, Gloria | 3500000 | Sep 2, 2014 | Feb. 2015 | 100% | 3499898.47 |  | Completed; for submission of liquidation to COA
DSWD IV- B Social Pension Fund (for the 1st & 2nd Quarter of 2014) | 27 brgys | 726000 | Aug. 20, 2014 | Dec. 2014 | 100% | 468000 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P258,000.00 was refunded to DSWD
DILG Performance Challenge Fund - Municipal Museum cum Tourism Center | Poblacion, Gloria | 1000000 | Jul. 31, 2014 | Dec. 2014 | 100% | 1000000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA | 23
DSWD IV-B Cellphone Repair Training | 27 brgys | 50000 | Mar 26, 2014 | Dec. 2014 | 100% | 50000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV-B Livelihood on Nego Kart | 27 brgys | 500000 | April 10, 2014 | Dec. 2014 | 100% | 500000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA BFAR BUB Project - Integrated Coastal Resource Management | 8 coastal brgys | 1400000 | Feb. 12, 2014 | May 2014 | 100% | 1400000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
OPAPP/PAMANA - Electrification of Sitios Bungkarot & Alabigan | Brgy. Buong Lupa, Gloria | 1370000 | Jun 7, 2013 | Jul. 24, 2013 | 89.21% | 1222209.58 |  | On-going; submitted liquidation of 80% (or P1.096M) downloaded fund & waiting for Credit Notice from COA
DILG IV-B PAMANA - Opening of FTM road | Brgy. Buong Lupa, Gloria | 3000000 | May 29, 2013 | Dec. 21, 2013 | 100% | 2984913.03 |  | Completed; submitted liquidation for the P600,000 final funding & waiting for Credit Notice from COA; balance of P15,086.97 was refunded to DILG
DILG IV-B PAMANA - Concreting of FTM road | Brgy. Buong Lupa, Gloria | 2500000 | Jan 23, 2013 | Apr 30, 2013 | 100% | 2483448 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P16,552.00 was refunded to DILG
OPAPP/PAMANA - Construction of Multi-Purpose Pavement | Brgy. Buong Lupa, Gloria | 150000 | Sep. 12, 2012 | Dec. 18, 2012 | 80% | 120000 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on Dec2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Construction of Day Care Center | Brgy. Buong Lupa, Gloria | 200000 | Sep. 12, 2012 | Dec. 6, 2012 | 79.73% | 159459.29 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on Dec2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Concreting of FTM Road Phase I | Brgy. Buong Lupa, Gloria | 880000 | Sep. 10, 2012 | Dec. 19, 2012 | 70.65% | 621761.01 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on May2013 & waiting for Credit Notice from COA
OPAPP/PAMANA - Purchase of Health Equipment | Brgy. Buong Lupa, Gloria | 50000 | Jul 23, 2012 | Dec. 18, 2012 | 100% | 49204.32 |  | Completed; re-submitted liquidation after getting audit suggestion on 1st submission on Dec.2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Abaca Production & Development | Brgy. Buong Lupa, Gloria | 280000 | Jul 23, 2012 | May 20, 2013 | 100% | 278923.79 |  | Completed; re-submitted liquidation after getting audit suggestion on 1st submission on Dec.2012 & waiting for Credit Notice from COA
CHD IV-B Construction of TB DOTS Building | Poblacion, Gloria | 200000 | July 21, 2012 | Dec 2014 | 100% | 200000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DOH Facilities Enhancement Program (Water System) | Brgy. Buong Lupa, Gloria | 431780 | Dec. 2011 | Oct 2012 | 100% | 391710 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P40,070.00 was refunded to DOH
DSWD IV-B Supplemental Feeding Program | 27 brgys | 1832025 | Oct. 2011 | Oct 2012 | 100% | 1769483.28 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P62,541.72 was refunded to DSWD
DA IV-B Bagsakan Center | Public Market, Poblacion | 860000 | Oct. 2010 | Dec. 2012 | 100% | 830500.15 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P29,499.15 was refunded to DA-ORMAES
DA IV-B Farm to Market Road Rehabilitation | Brgys. Maragooc-Agsalin | 9964508.28 | Apr. 2010 | Dec. 2010 | 100% | 9964508.28 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA IV-B Farm to Market Road Rehabilitation | Brgys. Agos-Malamig | 9906611.19 | Apr. 2010 | Dec. 2010 | 100% | 9906611.19 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA IV-B Farm to Market Road Rehabilitation | Brgys. Maligaya-Agos | 9942118.52 | Apr. 2010 | Dec. 2010 | 100% | 9942118.52 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
RODERICK B. LOGDAT | [5 empty] | GERMAN D. RODEGERIO
Municipal Accountant | [5 empty] | Municipal Mayor

## TFUtil~3rdQtr2016
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 3RD QUARTER, CY 2016
MUNICIPAL GOVERNMENT OF GLORIA | [7 empty] | FDP Form 6 - Trust Fund Utilization
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
DOLE Vermiculture Fund with BOF Composting of GLOSAA | Brgy. Narra, Gloria | 650500 |  |  |  | 0 |  | For implementation CY2016
DSWD Supplemental Feeding Program Cycle 6 | 34 Day Care Centers | 3367800 | July 2016 |  | 14.29% | 481200 |  | Implementation in process
DA Integrated Community Food Production 2016 | 27 brgys | 5000000 | July 2016 |  | 15.06% | 753000 |  | Implementation in process
DA BUB Project - Irrigation Small Water Impounding Project | Brgy. Kawit, Gloria | 270000 | July 2016 | August 2016 | 100% | 268750 |  | Completed; in process of liquidation
DILG Region IVB - 2015 Salintubig Fund (Construction of Potable Water Supply) | Brgy. Guimbonan, Gloria | 2000000 | Apr 29, 2016 |  | 86.16% | 1723220.07 |  | Construction in progress
DILG Region IVB - 2015 Salintubig Fund (Construction of Potable Water Supply) | Brgy. Maragooc, Gloria | 2000000 | May 24, 2016 |  | 86.16% | 1723220.07 |  | Construction in progress
DILG Region IVB - 2015 Salintubig Fund (Construction of Potable Water Supply) | Brgy. Mirayan, Gloria | 1000000 | May 31, 2016 | July 2016 | 100% | 999999.16 |  | Completed; in process of liquidation
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Narra, Gloria | 500000 | Apr 29, 2016 |  | 83.4% | 416998.02 |  | Construction in progress
DILG Region IVB - 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. San Antonio, Gloria | 2800000 | Apr 26, 2016 |  | 81.82% | 2291082.07 |  | Construction in progress; 1st tranche P1.6M was liquidated; with P800,000 LGU counterpart
DILG Region IVB - 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. Maligaya, Gloria | 2655000 | March 31, 2016 |  | 75.76% | 2011334.46 |  | Construction in progress; 1st tranche P1.644M was liquidated; with P595,000 LGU counterpart
DILG Region IVB - 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. Agos, Gloria | 2580000 | March 31, 2016 |  | 70.26% | 1812741.84 |  | Construction in progress; 1st tranche P1.6M was liquidated; with P580,000 LGU counterpart
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Sta. Maria, Gloria | 1070000 | Apr 26, 2016 |  | 86.94% | 930285.6 |  | Construction in progress; with P320,000 LGU counterpart
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Banus, Gloria | 700000 | March 31, 2016 |  | 91.36% | 639485.5 |  | Construction in progress; with P180,000 LGU counterpart
DILG Region IVB - 2015 BUB Water Fund for Extension of Water System Level II | Brgy. Tambong, Gloria | 1000000 | Apr 29, 2016 |  | 39.21% | 392146.12 |  | Construction in progress; with P225,000 LGU counterpart
DILG Region IVB - 2014 GPBP Fund for road opening | Brgy. Malubay, Gloria | 450000 | Feb 29, 2016 | Apr 29, 2016 | 100% | 366258.6 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P83,741.40 was refunded to DILG
DILG Region IVB - 2014 GPBP Fund for road opening | Brgy. Alma Villa, Gloria | 1350000 | Feb 29, 2016 | Apr 29, 2016 | 100% | 1202719.6 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P147,280.40 was refunded to DILG
DSWD IV - B Construction of Day Care Centers | Brgy. M. Adriatico | 750000 | March 31, 2016 |  | 78.04% | 585326 |  | Construction in progress; 1st tranche P600,000 was liquidated; waiting for final tranche
DSWD IV - B Construction of Day Care Centers | Brgy. Manguyang | 750000 | March 31, 2016 |  | 79.63% | 597254 |  | Construction in progress; 1st tranche P600,000 was liquidated; waiting for final tranche
DSWD IV - B Construction of Day Care Centers | Brgy. Malayong | 800000 | Apr 26, 2016 |  | 74.86% | 598881.93 |  | Construction in progress; 1st tranche P640,000 was liquidated; waiting for final tranche
DSWD IV - B Construction of Day Care Centers | Brgy. Mirayan | 800000 | March 21, 2016 |  | 79.87% | 638922 |  | Construction in progress; 1st tranche P640,000 was liquidated; waiting for final tranche
DSWD IV- B Fund for Women Welfare Program under (GPB) | Poblacion, Gloria | 85000 | March 31, 2016 | April 26, 2016 | 100% | 85000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV - B Orientation & Planning Workshop on Child & Youth Welfare under GPB | Poblacion, Gloria | 85000 | May 24, 2016 | May 31, 2016 | 100% | 85000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DOH HFIP- Health Facilities Improvement Project (Phase 1) | Poblacion, Gloria | 3000000 | March 31, 2016 | August 2016 | 100% | 2998983.6 |  | Completed; in process of liquidation; with P1,500,000 LGU counterpart
DSWD IV- B Social Pension Fund (for the 3rd Quarter 2016) | 27 brgys | 2140500 | September 10, 2016 | September 29, 2016 | 100% | 2118000 |  | Completed; in process of liquidation
DSWD IV- B Social Pension Fund (for the 2nd Quarter 2016, w/ addtl Jan-Jun 2016) | 27 brgys | 2740500 | June 30, 2016 | July 2016 | 100% | 2721000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV- B Social Pension Fund (for the 1st Quarter 2016) | 27 brgys | 1540500 | March 31, 2016 | April 25, 2016 | 100% | 1369500 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV- B Social Pension Fund (1st - 4th Quarter 2015) | 27 brgys | 6162000 | Oct. 21, 2015 | Nov. 20, 2015 | 100% | 5759000 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P403,000 was refunded to DSWD
DSWD IV- B Social Pension Fund | 27 brgys | 258000 | Sept. 30, 2015 | Oct 2015 | 100% | 244500 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P13,500.00 was refunded to DSWD
DSWD IV- B Social Pension Fund (for the 3rd & 4th Quarter of 2014, w/ addtl in 1st & 2nd Qtr) | 27 brgys | 2844000 | May 30, 2015 | June 2015 | 100% | 2725500 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DOLE RO IV-B - Livelihood grant for Kawit Fish Processing | Brgy. Kawit, Gloria | 85000 | Feb. 2, 2015 | Mar 2015 | 100% | 85000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV-B Baking & Decorating Cakes | 27 brgys | 50000 | Jan. 30, 2015 | May 28, 2015 | 100% | 50000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DRRM Fund - Construction of MDRRM Operation Center | Poblacion, Gloria | 4012000 | Nov. 17, 2014 | Apr. 2015 | 100% | 4007103.25 |  | Completed construction of building
DSWD IV-B for the 2 Storey Women & Youth Livelihood & Recreational Center (BUB) | Poblacion, Gloria | 3500000 | Sep 2, 2014 | Feb. 2015 | 100% | 3499898.47 |  | Completed; for submission of liquidation to COA
DSWD IV- B Social Pension Fund (for the 1st & 2nd Quarter of 2014) | 27 brgys | 726000 | Aug. 20, 2014 | Dec. 2014 | 100% | 468000 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P258,000.00 was refunded to DSWD
DILG Performance Challenge Fund - Municipal Museum cum Tourism Center | Poblacion, Gloria | 1000000 | Jul. 31, 2014 | Dec. 2014 | 100% | 1000000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA | 23
DSWD IV-B Cellphone Repair Training | 27 brgys | 50000 | Mar 26, 2014 | Dec. 2014 | 100% | 50000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV-B Livelihood on Nego Kart | 27 brgys | 500000 | April 10, 2014 | Dec. 2014 | 100% | 500000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA BFAR BUB Project - Integrated Coastal Resource Management | 8 coastal brgys | 1400000 | Feb. 12, 2014 | May 2014 | 100% | 1400000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
OPAPP/PAMANA - Electrification of Sitios Bungkarot & Alabigan | Brgy. Buong Lupa, Gloria | 1370000 | Jun 7, 2013 | Jul. 24, 2013 | 89.21% | 1222209.58 |  | On-going; submitted liquidation of 80% (or P1.096M) downloaded fund & waiting for Credit Notice from COA
DILG IV-B PAMANA - Opening of FTM road | Brgy. Buong Lupa, Gloria | 3000000 | May 29, 2013 | Dec. 21, 2013 | 100% | 2984913.03 |  | Completed; submitted liquidation for the P600,000 final funding & waiting for Credit Notice from COA; balance of P15,086.97 was refunded to DILG
DILG IV-B PAMANA - Concreting of FTM road | Brgy. Buong Lupa, Gloria | 2500000 | Jan 23, 2013 | Apr 30, 2013 | 100% | 2483448 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P16,552.00 was refunded to DILG
OPAPP/PAMANA - Construction of Multi-Purpose Pavement | Brgy. Buong Lupa, Gloria | 150000 | Sep. 12, 2012 | Dec. 18, 2012 | 80% | 120000 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on Dec2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Construction of Day Care Center | Brgy. Buong Lupa, Gloria | 200000 | Sep. 12, 2012 | Dec. 6, 2012 | 79.73% | 159459.29 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on Dec2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Concreting of FTM Road Phase I | Brgy. Buong Lupa, Gloria | 880000 | Sep. 10, 2012 | Dec. 19, 2012 | 70.65% | 621761.01 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on May2013 & waiting for Credit Notice from COA
OPAPP/PAMANA - Purchase of Health Equipment | Brgy. Buong Lupa, Gloria | 50000 | Jul 23, 2012 | Dec. 18, 2012 | 100% | 49204.32 |  | Completed; re-submitted liquidation after getting audit suggestion on 1st submission on Dec.2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Abaca Production & Development | Brgy. Buong Lupa, Gloria | 280000 | Jul 23, 2012 | May 20, 2013 | 100% | 278923.79 |  | Completed; re-submitted liquidation after getting audit suggestion on 1st submission on Dec.2012 & waiting for Credit Notice from COA
CHD IV-B Construction of TB DOTS Building | Poblacion, Gloria | 200000 | July 21, 2012 | Dec 2014 | 100% | 200000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DOH Facilities Enhancement Program (Water System) | Brgy. Buong Lupa, Gloria | 431780 | Dec. 2011 | Oct 2012 | 100% | 391710 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P40,070.00 was refunded to DOH
DSWD IV-B Supplemental Feeding Program | 27 brgys | 1832025 | Oct. 2011 | Oct 2012 | 100% | 1769483.28 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P62,541.72 was refunded to DSWD
DA IV-B Bagsakan Center | Public Market, Poblacion | 860000 | Oct. 2010 | Dec. 2012 | 100% | 830500.15 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P29,499.15 was refunded to DA-ORMAES
DA IV-B Farm to Market Road Rehabilitation | Brgys. Maragooc-Agsalin | 9964508.28 | Apr. 2010 | Dec. 2010 | 100% | 9964508.28 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA IV-B Farm to Market Road Rehabilitation | Brgys. Agos-Malamig | 9906611.19 | Apr. 2010 | Dec. 2010 | 100% | 9906611.19 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA IV-B Farm to Market Road Rehabilitation | Brgys. Maligaya-Agos | 9942118.52 | Apr. 2010 | Dec. 2010 | 100% | 9942118.52 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
RODERICK B. LOGDAT | [5 empty] | GERMAN D. RODEGERIO
Municipal Accountant | [5 empty] | Municipal Mayor

## TFUtil~4thQtr2016
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 4th QUARTER, CY 2016
MUNICIPAL GOVERNMENT OF GLORIA | [7 empty] | FDP Form 6 - Trust Fund Utilization
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
DSWD Supplemental Feeding Program Cycle 6 | 34 Day Care Centers | 3367800 | July 2016 |  | 62.79% | 2114700 |  | Implementation in process
DA Integrated Community Food Production 2016 | 27 brgys | 5000000 | July 2016 |  | 41.97% | 2098615 |  | Implementation in process
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Narra, Gloria | 500000 | Apr 29, 2016 |  | 83.4% | 416998.02 |  | Construction in progress
DILG Region IVB - 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. San Antonio, Gloria | 2800000 | Apr 26, 2016 |  | 81.82% | 2291082.07 |  | Construction in progress; 1st tranche P1.6M was liquidated; with P800,000 LGU counterpart
DILG Region IVB - 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. Maligaya, Gloria | 2655000 | March 31, 2016 |  | 75.76% | 2011334.46 |  | Construction in progress; 1st tranche P1.644M was liquidated; with P595,000 LGU counterpart
DILG Region IVB - 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. Agos, Gloria | 2580000 | March 31, 2016 |  | 70.26% | 1812741.84 |  | Construction in progress; 1st tranche P1.6M was liquidated; with P580,000 LGU counterpart
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Sta. Maria, Gloria | 1070000 | Apr 26, 2016 |  | 86.94% | 930285.6 |  | Construction in progress; with P320,000 LGU counterpart
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Banus, Gloria | 700000 | March 31, 2016 |  | 91.36% | 639485.5 |  | Construction in progress; with P180,000 LGU counterpart
DILG Region IVB - 2015 BUB Water Fund for Extension of Water System Level II | Brgy. Tambong, Gloria | 1000000 | Apr 29, 2016 |  | 39.21% | 392146.12 |  | Construction in progress; with P225,000 LGU counterpart
DILG Region IVB - 2014 GPBP Fund for road opening | Brgy. Malubay, Gloria | 450000 | Feb 29, 2016 | Apr 29, 2016 | 100% | 366258.6 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P83,741.40 was refunded to DILG
DILG Region IVB - 2014 GPBP Fund for road opening | Brgy. Alma Villa, Gloria | 1350000 | Feb 29, 2016 | Apr 29, 2016 | 100% | 1202719.6 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P147,280.40 was refunded to DILG
DSWD IV - B Construction of Day Care Centers | Brgy. M. Adriatico | 750000 | March 31, 2016 |  | 99.76% | 748205.41 |  | Construction in progress; 1st tranche P600,000 was liquidated; final tranche being utilized for completion
DSWD IV - B Construction of Day Care Centers | Brgy. Manguyang | 750000 | March 31, 2016 |  | 99.56% | 746668 |  | Construction in progress; 1st tranche P600,000 was liquidated; final tranche being utilized for completion
DSWD IV - B Construction of Day Care Centers | Brgy. Malayong | 800000 | Apr 26, 2016 | December 2016 | 96.48% | 771862.93 |  | Completed; 1st tranche P640,000 was liquidated; final & total tranche for liquidation
DSWD IV - B Construction of Day Care Centers | Brgy. Mirayan | 800000 | March 21, 2016 | December 2016 | 86.63% | 693072 |  | Construction in progress; 1st tranche P640,000 was liquidated; waiting for final tranche
DA BUB Project - Irrigation Small Water Impounding Project | Brgy. Kawit, Gloria | 270000 | July 2016 | August 2016 | 100% | 268750 |  | Completed and liquidated
DILG Region IVB - 2015 Salintubig Fund (Construction of Potable Water Supply) | Brgy. Guimbonan, Gloria | 2000000 | Apr 29, 2016 | November 2016 | 100% | 1998803.55 |  | Completed and liquidated
DILG Region IVB - 2015 Salintubig Fund (Construction of Potable Water Supply) | Brgy. Maragooc, Gloria | 2000000 | May 24, 2016 | November 2016 | 100% | 1999061.46 |  | Completed and liquidated
DILG Region IVB - 2015 Salintubig Fund (Construction of Potable Water Supply) | Brgy. Mirayan, Gloria | 1000000 | May 31, 2016 | July 2016 | 100% | 999999.16 |  | Completed and liquidated
DSWD IV- B Social Pension Fund (for the 4th Quarter 2016) | 27 brgys | 2140500 | December 2016 | December 2016 | 100% | 2094000 |  | Completed and liquidated
DOLE Vermiculture Fund with BOF Composting of GLOSAA | Brgy. Narra, Gloria | 650500 |  | December 2016 | 100% | 650500 |  | Completed and liquidated
DSWD IV- B Fund for Women Welfare Program under (GPB) | Poblacion, Gloria | 85000 | March 31, 2016 | April 26, 2016 | 100% | 85000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV - B Orientation & Planning Workshop on Child & Youth Welfare under GPB | Poblacion, Gloria | 85000 | May 24, 2016 | May 31, 2016 | 100% | 85000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DOH HFIP- Health Facilities Improvement Project (Phase 1) | Poblacion, Gloria | 3000000 | March 31, 2016 | August 2016 | 100% | 2998983.6 |  | Completed; in process of liquidation; with P1,500,000 LGU counterpart
DSWD IV- B Social Pension Fund (for the 3rd Quarter 2016) | 27 brgys | 2140500 | September 10, 2016 | September 29, 2016 | 100% | 2118000 |  | Completed; in process of liquidation
DSWD IV- B Social Pension Fund (for the 2nd Quarter 2016, w/ addtl Jan-Jun 2016) | 27 brgys | 2740500 | June 30, 2016 | July 2016 | 100% | 2721000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV- B Social Pension Fund (for the 1st Quarter 2016) | 27 brgys | 1540500 | March 31, 2016 | April 25, 2016 | 100% | 1369500 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV- B Social Pension Fund (1st - 4th Quarter 2015) | 27 brgys | 6162000 | Oct. 21, 2015 | Nov. 20, 2015 | 100% | 5759000 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P403,000 was refunded to DSWD
DSWD IV- B Social Pension Fund | 27 brgys | 258000 | Sept. 30, 2015 | Oct 2015 | 100% | 244500 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P13,500.00 was refunded to DSWD
DSWD IV- B Social Pension Fund (for the 3rd & 4th Quarter of 2014, w/ addtl in 1st & 2nd Qtr) | 27 brgys | 2844000 | May 30, 2015 | June 2015 | 100% | 2725500 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DOLE RO IV-B - Livelihood grant for Kawit Fish Processing | Brgy. Kawit, Gloria | 85000 | Feb. 2, 2015 | Mar 2015 | 100% | 85000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV-B Baking & Decorating Cakes | 27 brgys | 50000 | Jan. 30, 2015 | May 28, 2015 | 100% | 50000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DRRM Fund - Construction of MDRRM Operation Center | Poblacion, Gloria | 4012000 | Nov. 17, 2014 | Apr. 2015 | 100% | 4007103.25 |  | Completed construction of building
DSWD IV-B for the 2 Storey Women & Youth Livelihood & Recreational Center (BUB) | Poblacion, Gloria | 3500000 | Sep 2, 2014 | Feb. 2015 | 100% | 3499898.47 |  | Completed; for submission of liquidation to COA
DSWD IV- B Social Pension Fund (for the 1st & 2nd Quarter of 2014) | 27 brgys | 726000 | Aug. 20, 2014 | Dec. 2014 | 100% | 468000 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P258,000.00 was refunded to DSWD
DILG Performance Challenge Fund - Municipal Museum cum Tourism Center | Poblacion, Gloria | 1000000 | Jul. 31, 2014 | Dec. 2014 | 100% | 1000000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA | 23
DSWD IV-B Cellphone Repair Training | 27 brgys | 50000 | Mar 26, 2014 | Dec. 2014 | 100% | 50000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV-B Livelihood on Nego Kart | 27 brgys | 500000 | April 10, 2014 | Dec. 2014 | 100% | 500000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA BFAR BUB Project - Integrated Coastal Resource Management | 8 coastal brgys | 1400000 | Feb. 12, 2014 | May 2014 | 100% | 1400000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
OPAPP/PAMANA - Electrification of Sitios Bungkarot & Alabigan | Brgy. Buong Lupa, Gloria | 1370000 | Jun 7, 2013 | Jul. 24, 2013 | 89.21% | 1222209.58 |  | On-going; submitted liquidation of 80% (or P1.096M) downloaded fund & waiting for Credit Notice from COA
DILG IV-B PAMANA - Opening of FTM road | Brgy. Buong Lupa, Gloria | 3000000 | May 29, 2013 | Dec. 21, 2013 | 100% | 2984913.03 |  | Completed; submitted liquidation for the P600,000 final funding & waiting for Credit Notice from COA; balance of P15,086.97 was refunded to DILG
DILG IV-B PAMANA - Concreting of FTM road | Brgy. Buong Lupa, Gloria | 2500000 | Jan 23, 2013 | Apr 30, 2013 | 100% | 2483448 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P16,552.00 was refunded to DILG
OPAPP/PAMANA - Construction of Multi-Purpose Pavement | Brgy. Buong Lupa, Gloria | 150000 | Sep. 12, 2012 | Dec. 18, 2012 | 80% | 120000 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on Dec2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Construction of Day Care Center | Brgy. Buong Lupa, Gloria | 200000 | Sep. 12, 2012 | Dec. 6, 2012 | 79.73% | 159459.29 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on Dec2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Concreting of FTM Road Phase I | Brgy. Buong Lupa, Gloria | 880000 | Sep. 10, 2012 | Dec. 19, 2012 | 70.65% | 621761.01 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on May2013 & waiting for Credit Notice from COA
OPAPP/PAMANA - Purchase of Health Equipment | Brgy. Buong Lupa, Gloria | 50000 | Jul 23, 2012 | Dec. 18, 2012 | 100% | 49204.32 |  | Completed; re-submitted liquidation after getting audit suggestion on 1st submission on Dec.2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Abaca Production & Development | Brgy. Buong Lupa, Gloria | 280000 | Jul 23, 2012 | May 20, 2013 | 100% | 278923.79 |  | Completed; re-submitted liquidation after getting audit suggestion on 1st submission on Dec.2012 & waiting for Credit Notice from COA
CHD IV-B Construction of TB DOTS Building | Poblacion, Gloria | 200000 | July 21, 2012 | Dec 2014 | 100% | 200000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DOH Facilities Enhancement Program (Water System) | Brgy. Buong Lupa, Gloria | 431780 | Dec. 2011 | Oct 2012 | 100% | 391710 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P40,070.00 was refunded to DOH
DSWD IV-B Supplemental Feeding Program | 27 brgys | 1832025 | Oct. 2011 | Oct 2012 | 100% | 1769483.28 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P62,541.72 was refunded to DSWD
DA IV-B Bagsakan Center | Public Market, Poblacion | 860000 | Oct. 2010 | Dec. 2012 | 100% | 830500.15 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P29,499.15 was refunded to DA-ORMAES
DA IV-B Farm to Market Road Rehabilitation | Brgys. Maragooc-Agsalin | 9964508.28 | Apr. 2010 | Dec. 2010 | 100% | 9964508.28 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA IV-B Farm to Market Road Rehabilitation | Brgys. Agos-Malamig | 9906611.19 | Apr. 2010 | Dec. 2010 | 100% | 9906611.19 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA IV-B Farm to Market Road Rehabilitation | Brgys. Maligaya-Agos | 9942118.52 | Apr. 2010 | Dec. 2010 | 100% | 9942118.52 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
RODERICK B. LOGDAT | [5 empty] | GERMAN D. RODEGERIO
Municipal Accountant | [5 empty] | Municipal Mayor

## TFUtil~1stQtr2017
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 1st QUARTER, CY 2017
MUNICIPAL GOVERNMENT OF GLORIA | [7 empty] | FDP Form 6 - Trust Fund Utilization
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
DA Integrated Community Food Production 2016 | 27 brgys | 5000000 | July 2016 |  | 41.97% | 2098615 |  | Implementation in process
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Narra, Gloria | 500000 | Apr 29, 2016 |  | 83.4% | 416998.02 |  | Construction in progress
DILG Region IVB - 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. San Antonio, Gloria | 2800000 | Apr 26, 2016 |  | 81.82% | 2291082.07 |  | Construction in progress; 1st tranche P1.6M was liquidated; with P800,000 LGU counterpart
DILG Region IVB - 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. Maligaya, Gloria | 2655000 | March 31, 2016 |  | 75.76% | 2011334.46 |  | Construction in progress; 1st tranche P1.644M was liquidated; with P595,000 LGU counterpart
DILG Region IVB - 2015 BUB Water Fund for Construction of Pump Extension of Water System Level II | Brgy. Agos, Gloria | 2580000 | March 31, 2016 |  | 70.26% | 1812741.84 |  | Construction in progress; 1st tranche P1.6M was liquidated; with P580,000 LGU counterpart
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Sta. Maria, Gloria | 1070000 | Apr 26, 2016 |  | 86.94% | 930285.6 |  | Construction in progress; with P320,000 LGU counterpart
DILG Region IVB - 2015 BUB Water Fund for Construction of Water System Level I | Brgy. Banus, Gloria | 700000 | March 31, 2016 |  | 91.36% | 639485.5 |  | Construction in progress; with P180,000 LGU counterpart
DILG Region IVB - 2015 BUB Water Fund for Extension of Water System Level II | Brgy. Tambong, Gloria | 1000000 | Apr 29, 2016 |  | 39.21% | 392146.12 |  | Construction in progress; with P225,000 LGU counterpart
DILG Region IVB - 2014 GPBP Fund for road opening | Brgy. Malubay, Gloria | 450000 | Feb 29, 2016 | Apr 29, 2016 | 100% | 366258.6 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P83,741.40 was refunded to DILG
DILG Region IVB - 2014 GPBP Fund for road opening | Brgy. Alma Villa, Gloria | 1350000 | Feb 29, 2016 | Apr 29, 2016 | 100% | 1202719.6 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P147,280.40 was refunded to DILG
DSWD IV - B Construction of Day Care Centers | Brgy. M. Adriatico | 750000 | March 31, 2016 |  | 99.76% | 748205.41 |  | Construction in progress; 1st tranche P600,000 was liquidated; final tranche being utilized for completion
DSWD IV - B Construction of Day Care Centers | Brgy. Manguyang | 750000 | March 31, 2016 |  | 99.56% | 746668 |  | Construction in progress; 1st tranche P600,000 was liquidated; final tranche being utilized for completion
DSWD IV - B Construction of Day Care Centers | Brgy. Malayong | 800000 | Apr 26, 2016 | December 2016 | 96.48% | 771862.93 |  | Completed; 1st tranche P640,000 was liquidated; final & total tranche for liquidation
DSWD IV - B Construction of Day Care Centers | Brgy. Mirayan | 800000 | March 21, 2016 | December 2016 | 86.63% | 693072 |  | Construction in progress; 1st tranche P640,000 was liquidated; waiting for final tranche
DA BUB Project - Irrigation Small Water Impounding Project | Brgy. Kawit, Gloria | 270000 | July 2016 | August 2016 | 100% | 268750 |  | Completed and liquidated
DILG Region IVB - 2015 Salintubig Fund (Construction of Potable Water Supply) | Brgy. Guimbonan, Gloria | 2000000 | Apr 29, 2016 | November 2016 | 100% | 1998803.55 |  | Completed and liquidated
DILG Region IVB - 2015 Salintubig Fund (Construction of Potable Water Supply) | Brgy. Maragooc, Gloria | 2000000 | May 24, 2016 | November 2016 | 100% | 1999061.46 |  | Completed and liquidated
DILG Region IVB - 2015 Salintubig Fund (Construction of Potable Water Supply) | Brgy. Mirayan, Gloria | 1000000 | May 31, 2016 | July 2016 | 100% | 999999.16 |  | Completed and liquidated
DSWD IV- B Social Pension Fund (for the 4th Quarter 2016) | 27 brgys | 2140500 | December 2016 | December 2016 | 100% | 2094000 |  | Completed and liquidated
DOLE Vermiculture Fund with BOF Composting of GLOSAA | Brgy. Narra, Gloria | 650500 |  | December 2016 | 100% | 650500 |  | Completed and liquidated
DSWD IV- B Fund for Women Welfare Program under (GPB) | Poblacion, Gloria | 85000 | March 31, 2016 | April 26, 2016 | 100% | 85000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV - B Orientation & Planning Workshop on Child & Youth Welfare under GPB | Poblacion, Gloria | 85000 | May 24, 2016 | May 31, 2016 | 100% | 85000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DOH HFIP- Health Facilities Improvement Project (Phase 1) | Poblacion, Gloria | 3000000 | March 31, 2016 | August 2016 | 100% | 2998983.6 |  | Completed; in process of liquidation; with P1,500,000 LGU counterpart
DSWD Supplemental Feeding Program Cycle 6 | 34 Day Care Centers | 3367800 | July 2016 | December 2016 | 62.79% | 2114700 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P46,500.00 was refunded to DSWD
DSWD IV- B Social Pension Fund (for the 3rd Quarter 2016) | 27 brgys | 2140500 | September 10, 2016 | November 2016 | 100% | 2140500 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV- B Social Pension Fund (for the 2nd Quarter 2016, w/ addtl Jan-Jun 2016) | 27 brgys | 2740500 | June 30, 2016 | July 2016 | 100% | 2721000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV- B Social Pension Fund (for the 1st Quarter 2016) | 27 brgys | 1540500 | March 31, 2016 | April 25, 2016 | 100% | 1369500 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV- B Social Pension Fund (1st - 4th Quarter 2015) | 27 brgys | 6162000 | Oct. 21, 2015 | Nov. 20, 2015 | 100% | 5759000 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P403,000 was refunded to DSWD
DSWD IV- B Social Pension Fund | 27 brgys | 258000 | Sept. 30, 2015 | Oct 2015 | 100% | 244500 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P13,500.00 was refunded to DSWD
DSWD IV- B Social Pension Fund (for the 3rd & 4th Quarter of 2014, w/ addtl in 1st & 2nd Qtr) | 27 brgys | 2844000 | May 30, 2015 | June 2015 | 100% | 2725500 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DOLE RO IV-B - Livelihood grant for Kawit Fish Processing | Brgy. Kawit, Gloria | 85000 | Feb. 2, 2015 | Mar 2015 | 100% | 85000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV-B Baking & Decorating Cakes | 27 brgys | 50000 | Jan. 30, 2015 | May 28, 2015 | 100% | 50000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DRRM Fund - Construction of MDRRM Operation Center | Poblacion, Gloria | 4012000 | Nov. 17, 2014 | Apr. 2015 | 100% | 4007103.25 |  | Completed construction of building
DSWD IV-B for the 2 Storey Women & Youth Livelihood & Recreational Center (BUB) | Poblacion, Gloria | 3500000 | Sep 2, 2014 | Feb. 2015 | 100% | 3499898.47 |  | Completed; for submission of liquidation to COA
DSWD IV- B Social Pension Fund (for the 1st & 2nd Quarter of 2014) | 27 brgys | 726000 | Aug. 20, 2014 | Dec. 2014 | 100% | 468000 |  | Completed; submitted liquidation to COA; waiting for Credit Notice; balance of P258,000.00 was refunded to DSWD
DILG Performance Challenge Fund - Municipal Museum cum Tourism Center | Poblacion, Gloria | 1000000 | Jul. 31, 2014 | Dec. 2014 | 100% | 1000000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA | 23
DSWD IV-B Cellphone Repair Training | 27 brgys | 50000 | Mar 26, 2014 | Dec. 2014 | 100% | 50000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DSWD IV-B Livelihood on Nego Kart | 27 brgys | 500000 | April 10, 2014 | Dec. 2014 | 100% | 500000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA BFAR BUB Project - Integrated Coastal Resource Management | 8 coastal brgys | 1400000 | Feb. 12, 2014 | May 2014 | 100% | 1400000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
OPAPP/PAMANA - Electrification of Sitios Bungkarot & Alabigan | Brgy. Buong Lupa, Gloria | 1370000 | Jun 7, 2013 | Jul. 24, 2013 | 89.21% | 1222209.58 |  | On-going; submitted liquidation of 80% (or P1.096M) downloaded fund & waiting for Credit Notice from COA
DILG IV-B PAMANA - Opening of FTM road | Brgy. Buong Lupa, Gloria | 3000000 | May 29, 2013 | Dec. 21, 2013 | 100% | 2984913.03 |  | Completed; submitted liquidation for the P600,000 final funding & waiting for Credit Notice from COA; balance of P15,086.97 was refunded to DILG
DILG IV-B PAMANA - Concreting of FTM road | Brgy. Buong Lupa, Gloria | 2500000 | Jan 23, 2013 | Apr 30, 2013 | 100% | 2483448 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P16,552.00 was refunded to DILG
OPAPP/PAMANA - Construction of Multi-Purpose Pavement | Brgy. Buong Lupa, Gloria | 150000 | Sep. 12, 2012 | Dec. 18, 2012 | 80% | 120000 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on Dec2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Construction of Day Care Center | Brgy. Buong Lupa, Gloria | 200000 | Sep. 12, 2012 | Dec. 6, 2012 | 79.73% | 159459.29 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on Dec2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Concreting of FTM Road Phase I | Brgy. Buong Lupa, Gloria | 880000 | Sep. 10, 2012 | Dec. 19, 2012 | 70.65% | 621761.01 |  | On-going; re-submitted liquidation of 80% downloaded fund after getting audit suggestion on 1st submission on May2013 & waiting for Credit Notice from COA
OPAPP/PAMANA - Purchase of Health Equipment | Brgy. Buong Lupa, Gloria | 50000 | Jul 23, 2012 | Dec. 18, 2012 | 100% | 49204.32 |  | Completed; re-submitted liquidation after getting audit suggestion on 1st submission on Dec.2012 & waiting for Credit Notice from COA
OPAPP/PAMANA - Abaca Production & Development | Brgy. Buong Lupa, Gloria | 280000 | Jul 23, 2012 | May 20, 2013 | 100% | 278923.79 |  | Completed; re-submitted liquidation after getting audit suggestion on 1st submission on Dec.2012 & waiting for Credit Notice from COA
CHD IV-B Construction of TB DOTS Building | Poblacion, Gloria | 200000 | July 21, 2012 | Dec 2014 | 100% | 200000 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DOH Facilities Enhancement Program (Water System) | Brgy. Buong Lupa, Gloria | 431780 | Dec. 2011 | Oct 2012 | 100% | 391710 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P40,070.00 was refunded to DOH
DSWD IV-B Supplemental Feeding Program | 27 brgys | 1832025 | Oct. 2011 | Oct 2012 | 100% | 1769483.28 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P62,541.72 was refunded to DSWD
DA IV-B Bagsakan Center | Public Market, Poblacion | 860000 | Oct. 2010 | Dec. 2012 | 100% | 830500.15 |  | Completed; submitted liquidation & waiting for Credit Notice from COA; balance of P29,499.15 was refunded to DA-ORMAES
DA IV-B Farm to Market Road Rehabilitation | Brgys. Maragooc-Agsalin | 9964508.28 | Apr. 2010 | Dec. 2010 | 100% | 9964508.28 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA IV-B Farm to Market Road Rehabilitation | Brgys. Agos-Malamig | 9906611.19 | Apr. 2010 | Dec. 2010 | 100% | 9906611.19 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
DA IV-B Farm to Market Road Rehabilitation | Brgys. Maligaya-Agos | 9942118.52 | Apr. 2010 | Dec. 2010 | 100% | 9942118.52 |  | Completed; submitted liquidation & waiting for Credit Notice from COA
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
RODERICK B. LOGDAT | [5 empty] | GERMAN D. RODEGERIO
Municipal Accountant | [5 empty] | Municipal Mayor