## 4th quarter
FDPP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2019
Province, City or Municipality: Gloria, Oriental Mindoro
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date |  |  | 49200
SOCIAL SERVICES SECTOR
Solid Waste Management Services
Construction of Additional SLF Facilities (Phase II) and repair & maintenance of SLF (CY) | Brgy. Agos | 5000000 | 4-3-2019 | 12-31-2019 | 90.17% | 4508746.99
Suma-Landfill Nawa (SLN) ang Basura ng Gloria Project (Operation of Sanitary Landfill Category I) PY | Brgy. Agos | 338925.12 | 8-6-2018 | 12-31-2019 | 2.499% | 8470
Construction of Communal Latrine and Installation of Water System
Unit of Communal Latrine with Male and Female Sections Constructed with Water System installed in Agsalin | Brgy. Agsalin | 255000 | 11-25-19 | 12-12-2019 | 97.92% | 249700
Provision of Level 1 Water System in various barangay | various Brgy. | 1000000 | 12-04-19 | 12-31-2019 | 99.67% | 996749.5
Total Social Services Sector |  | 5338925.12 |  |  |  | 4517216.99
ENVIRONMENTAL SERVICE SECTOR
ECONOMIC SERVICES SECTOR
Engineering Services - Construction and Maintenance
Establishment of Municipal Museum | Maligaya,Gloria | 151664 | 8-15-18 | 12-30-18 | 99.67% | 151160
Capital Expenditure for Local Economic Development Project: Improvement of Municipal Plaza-cum-Kubotel | Maligaya,Gloria | 1069814.5 |  |  | 99.9% | 1068788.5
Construction of Sitio Townsite Multi-Purpose Hall at Brgy. Malubay | Brgy.Malubay | 131464 | 10-9-18 | 12-26-18 | 97.76% | 128525
Construction of Multi-Purpose Building-cum-Evacuation Center at Sta. Maria Phase II(2018) | Brgy.Sta. Maria | 12650 | 10-10-2017 | 12-22-2018 | 100% | 12650
Sta. Theresa Protection Dike | Brgy. Sta.Theresa | 500000 | 7-12-18 | 12-28-18 | 99.92% | 499620
Drainage Canal Construction | Brgy. Bulaklakan | 127095.03 | 7-20-18 | 12-28-18 | 97.83% | 124336.1
Capital Expenditure for Livelihood Projects(2018) | Mun.farm Maligaya,Gloria | 82692.42 | 7-20-18 | 12-28-18 | 96.9% | 80132.5
Const. of MP Hall - Sta Maria (SB2018) | Brgy.Sta. Maria | 556299.2 | 5-28-19 | 12-31-19 | 99.87% | 555590
Construction of Bulakalakan MP-Hall | Brgy. Bulaklakan | 140000 | 8-10-18 | 12-20-18 | 99.8% | 139719.6
Rehab & Improve SC Hall - Sta Theresa | Brgy. Sta.Theresa | 250000 | 8-05-18 | 12-30-18 | 99.9% | 249739
Drainage Canal Construction - Alma Villa | Brgy. Alma Villa | 250000 | 1-20-18 | 12-31-18 | 99.68% | 249204.75
Municipal Counterpart for LGU-Led KC-NCDDP Implementation of Sub-Projects | Various brgys. | 2880000 | 11-15-18 | 12-31-18 | 84.49% | 2433268.12
Construction of Manpower Development Center: Employment and Livelihood Training Center |  | 1100000 | 6-28-2019 | 12-31-2019 | 100% | 1100000
Sapat Dapat Project- LGU Loan Amortization to LBP- Lending Center(AB 2019) | Maligaya,Gloria | 4814000 | 4-12-2019 | 12-31-2019 | 100% | 4814000
Multi-Purpose Building cum Evacuatioon Center Project - Malubay | Brgy. Malubay | 1000000 | 5-5-2019 | 12-31-2019 | 99.76% | 997637
Construction and Improvement of Multi-Purpose Building - M. Adriatico | Brgy. M. adriatico | 1000000 | 5-5-2019 | 12-31-2019 | 99.76% | 997637
Additional Fund for Purchase of Relocation Land | Various brgys. | 750000 | 7/10/2019 | 12-31-2019 | 28% | 210000
Road Concreting Sito Sta Ana to Core Housing Barangay Balete | Brgy. Balete | 1000000 | 10-5-2019- | 12-31-2019 | 99.88% | 998760
Construction and Improvement of Multi-Purpose Building - Agsalin | Brgy. Agsalin | 3250000 | 7/12/2019 | 12-31-2019 | 99.83% | 3244312.5
Multi-Purpose Building cum Evacuatioon Center Project - Maragooc | Brgy. Maragooc | 3250000 | 7/20/2019 | 12-31-2019 | 69.87% | 2270633.53
Multi-Purpose Building cum Evacuatioon Center Project - Sta. Theresa | Brgy. Sta.Theresa | 3250000 | 7/10/2019 | 12-31-2019 | 99.88% | 3246118.05
Multi-Purpose Building cum Evacuation Center Project - Bulaklakan | Brgy. Bulaklakan | 3250000 | 7/12/2019 | 12-31-2019 | 99.93% | 3247800
Improvement of Malamig Multi-Purpose Hall-cum Evacuation Center | Brgy. Malamig | 380299.93 | 7/8/2019 | 12-31-2019 | 99.78% | 379445
Multi-Purpose Building cum Evacuatioon Center Project - Sta. Maria | Brgy.Sta. Maria | 686000 | 7/15/2019 | 12-31-2019 | 89.05% | 610850
Capital Expenditure for Local Economic Development Project: Construction of Municipal Plaza Freedom Park (2019) |  | 1500000 | 7/6/2019 | 12/31/2019 | 91.64% | 1374586.25
Construction of Box Culvert/Spillway-Manguyang | Brgy. Manguyang | 500000 | 10-16-19 | 12-21-2019 | 94.74% | 473686
Agriculture Services
Capital Expenditure for Livelihood Projects(2015) | Maligaya Gloria | 157180 | 8-05-18 | 12-30-18 | 100% | 157180
TOTAL Economic Services Sector |  | 32039159.08 |  |  |  | 29815378.9
TOTAL |  | 37378084.2 |  |  |  | 34332595.89
Prepared by: |  |  |  |  | Certified correct:
SHERALEEN C. ABUAN | [5 empty] | GERMAN D. RODEGERIO
Municipal Budget Officer | [5 empty] | Municipal Mayor
Note on C7: Gloria: APPROPRIATION/ bal.of dec. 31 2018